## Executive Dashboard
ALTIJARA MAGAZINE TRANSFORMATION · EXECUTIVE DASHBOARD
Client: O2 Nations · Solo Full-Stack Developer · Build 12–25 Oct · QA & Deployment Prep 26–31 Oct · Final deadline 1 Nov 2026
| Production (do not touch): |  |  | https://altijaramagazine.com/ |  |  |  |  | Staging (all work here): |  |  | https://chocolate-jellyfish-822708.hostingersite.com/
| Go to ▸ | Master | P1 | P2 | P3 | P4 | P5 | P6 | QA | Deploy | Risks | Req Map
CONTROL PANEL (yellow cells are editable — everything else is calculated)
| Status date override |  |  |  | Effective status date |  | 2026-10-11 |  |  |  | Final deadline |  | 2026-11-01
PROGRESS OVERVIEW
| OVERALL COMPLETION |  |  | PLANNED BY STATUS DATE |  |  | SCHEDULE VARIANCE |  |  | DAYS TO 1 NOV |  |  | SCHEDULE HEALTH
| 1.802% |  |  | 0% |  |  | 1.802% |  |  | 21 |  |  | ON TRACK
| average task completion |  |  | baseline schedule |  |  | actual − planned |  |  | calendar days |  |  | overdue, blocked & variance
Overall █░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░ 2% ¦ Planned 0%
| TOTAL TASKS |  | COMPLETED |  | IN PROGRESS |  | NOT STARTED |  | REVIEW / TESTING |  | BLOCKED |  | OVERDUE |  | OPEN P0
| 111 |  | 2 |  | 0 |  | 109 |  | 0 |  | 0 |  | 0 |  | 71
| in scope |  | 2% of tasks |  | 0% of tasks |  | 98% of tasks |  | 0% of tasks |  | 0% of tasks |  | 0% of tasks |  | 64% of tasks
PHASE PROGRESS (click a phase name to open its tracker)
| Phase | Phase name |  |  | Window | Tasks | Done | Blocked | Overdue | In Prog. | Open P0 | Planned % | Actual % | Progress |  | Health
| P1 | Theme Foundation & Asset Pipeline |  |  | 12 Oct – 14 Oct | 17 | 2 | 0 | 0 | 0 | 12 | 0% | 11.76% | ██░░░░░░░░░░░░ |  | On Track
| P2 | Homepage & Dynamic Section Manager |  |  | 15 Oct – 17 Oct | 24 | 0 | 0 | 0 | 0 | 11 | 0% | 0% | ░░░░░░░░░░░░░░ |  | Not Started
| P3 | Editorial & Taxonomy Templates |  |  | 18 Oct – 20 Oct | 16 | 0 | 0 | 0 | 0 | 8 | 0% | 0% | ░░░░░░░░░░░░░░ |  | Not Started
| P4 | Digital Issues Archive & CPT Engine |  |  | 12 Oct – 22 Oct | 12 | 0 | 0 | 0 | 0 | 9 | 0% | 0% | ░░░░░░░░░░░░░░ |  | Not Started
| P5 | Auth, Subscriptions, AdOps & Leads |  |  | 12 Oct – 25 Oct | 20 | 0 | 0 | 0 | 0 | 11 | 0% | 0% | ░░░░░░░░░░░░░░ |  | Not Started
| P6 | Database Cleanup, Crawl Audit & Cutover |  |  | 12 Oct – 01 Nov | 22 | 0 | 0 | 0 | 0 | 20 | 0% | 0% | ░░░░░░░░░░░░░░ |  | Not Started
| TOTAL |  |  |  |  | 111 | 2 | 0 | 0 | 0 | 71 | 0% | 1.802%
| PRIORITY BREAKDOWN | [7 empty] | STATUS MIX |  |  |  | OPEN EXTERNAL DEPENDENCIES
| Priority |  |  | Tasks | Completed | Open | % Done |  | Status | Count | % |  | Type |  | Open | Next due
| P0 · Must-have for launch |  |  | 73 | 2 | 71 | 2.74% |  | Not Started | 109 | 98.2% |  | Credentials |  | 6 | 2026-10-13
| P1 · Important |  |  | 34 | 0 | 34 | 0% |  | In Progress | 0 | 0% |  | Payment Approval |  | 3 | 2026-10-22
| P2 · Nice-to-have / deferrable |  |  | 4 | 0 | 4 | 0% |  | Blocked | 0 | 0% |  | Historical Assets |  | 1 | 2026-10-20
[9 empty] | In Review | 0 | 0% |  | Server Access |  | 9 | 2026-10-12
| ✓ No overdue or blocked tasks. | [7 empty] | Testing | 0 | 0% |  | Client Content |  | 4 | 2026-10-25
[9 empty] | Completed | 2 | 1.802%
[9 empty] | Overdue | 0 | 0%
CHARTS (update automatically from the Master Tracker)
| UPCOMING DEADLINES (next open tasks by due date) | [8 empty] | CRITICAL BLOCKERS (Blocked status or blocker text)
| ID | Task |  |  | Phase | Due | Days | Status |  | ID | Task |  | Status | Blocker / Issue
| P1-03 | Theme setup: supports, menus, image sizes |  |  | Phase 1 | 2026-10-12 | 1 | Not Started | [8 empty] | 3
| P1-04 | Asset enqueue, versioning & conditional loading |  |  | Phase 1 | 2026-10-12 | 1 | Not Started | [8 empty] | 4
| P1-05 | Base template hierarchy |  |  | Phase 1 | 2026-10-12 | 1 | Not Started | [8 empty] | 5
| P1-06 | Reusable template-part components |  |  | Phase 1 | 2026-10-12 | 1 | Not Started | [8 empty] | 6
| P6-01 | Full production backup (files + DB) before any work |  |  | Phase 6 | 2026-10-12 | 1 | Not Started | [8 empty] | 90
| P6-02 | Verify staging mirrors production |  |  | Phase 6 | 2026-10-12 | 1 | Not Started | [8 empty] | 91
| P1-07 | CSS architecture & design tokens |  |  | Phase 1 | 2026-10-13 | 2 | Not Started | [8 empty] | 7
| P1-08 | Vanilla JS module architecture |  |  | Phase 1 | 2026-10-13 | 2 | Not Started | [8 empty] | 8
| P1-09 | RTL layout & Arabic typography |  |  | Phase 1 | 2026-10-13 | 2 | Not Started | [8 empty] | 9
| P1-10 | Responsive grid & breakpoints |  |  | Phase 1 | 2026-10-13 | 2 | Not Started | [8 empty] | 10
✓ No blockers recorded
HOW TO USE
1. Update Status, Completion %, Actual Hours and Completion Date only in the Master Tracker (white / yellow cells). Every other sheet updates automatically.
2. Columns headed with ƒ (gray cells) are formulas — do not type over them. Yellow cells are editable inputs.
3. Overall completion = average of all tasks: Completed = 100%, Not Started = 0%, otherwise the Completion % you enter (capped at 99%).
4. Planned % = how far each task is through its Start→Due window on the status date. Change dates in the Master Tracker to re-baseline.
5. Source note: built from the project brief. The 13-page Engineering Directive PDF was not available when generated — reconcile acceptance criteria against it (Risk R-01).
6. Spare blank rows at the bottom of the Master Tracker are pre-wired for new tasks: give them an ID like P3-17 and a Phase, and they flow into every view.
Formulas:
P5 = IF([P1]="",TODAY(),[P1])
Health = IF([OPEN P0]=0,"—",MINIFS('Master Tracker'!$I6:I400,'Master Tracker'!$S6:S400,"Credentials",'Master Tracker'!$G6:G400,"<>Completed"))
Health = IF([OPEN P0]=0,"—",MINIFS('Master Tracker'!$I6:I400,'Master Tracker'!$S6:S400,"Payment Approval",'Master Tracker'!$G6:G400,"<>Completed"))
Note on D7: Leave blank to use today's date. Enter a date to view the project 'as of' that day.

## Master Tracker
MASTER PROJECT TRACKER · single source of truth
Edit tasks here only — dashboard, phase sheets and requirement map recalculate automatically.
Legend: | Editable | ƒ Calculated | Status colors → | Completed · In Progress · In Review / Testing · Blocked / Overdue · Not Started |  | ← Dashboard |  | Staging ↗ |  | Live ↗
Task ID | Phase ▾ | Module ▾ | Task Name | Detailed Description | Priority ▾ | Status ▾ | Start Date ▾ | Due Date ▾ | Completion % ▾ | Dependencies ▾ | Environment ▾ | Related WordPress Files | Testing Checklist | Acceptance Criteria | Blocker / Issue ▾ | Notes ▾ | Completion Date ▾ | External Requirement ▾ | Test Result ▾ | ƒ Effective % | ƒ Planned % | ƒ Days Left | ƒ Overdue | ƒ Dependency Check | ƒ Phase Key | ƒ Upcoming Key | ƒ Blocker Key | ƒ Alert
P1-01 | Phase 1 | Staging Setup | Staging environment readiness audit | Confirm Hostinger staging access (hPanel, SFTP/SSH, phpMyAdmin), PHP 8.1+, WordPress & plugin versions, memory limits; enable WP_DEBUG_LOG; block indexing (noindex + password/IP protection); disable or trap outgoing mail so staging never emails real readers. | P0 | Completed | 2026-10-12 | 2026-10-12 | 0% | P6-02 | Staging (Hostinger) | wp-config.php, .htaccess | Log in via hPanel, SFTP and phpMyAdmin; confirm noindex header; send test mail is trapped | Staging is reachable only by the team, not indexed, debug logging active, versions documented in Notes |  |  |  | Server Access | Not Tested | 100% | 0% |  |  | ⏳ 1 open | Phase 1¦1 |  |  | Done
P1-02 | Phase 1 | Theme Scaffold | Create custom theme structure + Git repo | Create /wp-content/themes/altijara/ with style.css header (Text Domain altijara, RTL), functions.php loader, inc/, template-parts/, assets/{css,js,fonts,img}, languages/. Initialise a remote Git repository for the theme as the backup of all staging work (no local environment). | P0 | Completed | 2026-10-12 | 2026-10-12 | 0% | P1-01 | Staging (Hostinger) | style.css, functions.php, inc/, template-parts/, assets/ | Theme listed in Appearance > Themes; activates with no PHP notices; first commit pushed | Folder structure in place, theme activates cleanly on staging, repository holds initial commit |  |  |  | None | Not Tested | 100% | 0% |  |  | ✓ Ready | Phase 1¦2 |  |  | Done
P1-03 | Phase 1 | Theme Initialization | Theme setup: supports, menus, image sizes | inc/setup.php: add_theme_support (title-tag, post-thumbnails, html5, custom-logo, responsive-embeds, align-wide, editor-styles); register_nav_menus (primary, top-bar, footer, mobile); add_image_size (hero, card, thumb, issue-cover); load_theme_textdomain; content_width. | P0 | Not Started | 2026-10-12 | 2026-10-12 | 0% | P1-02 | Staging (Hostinger) | inc/setup.php, functions.php | Menus appear in Appearance > Menus; new upload generates all image sizes; single <title> tag | All supports, menus and image sizes registered; no duplicate title tags |  |  |  | None | Not Tested | 0% | 0% | 1 |  | ✓ Ready | Phase 1¦3 | 46307.0001 |  | Due soon
P1-04 | Phase 1 | Asset Pipeline | Asset enqueue, versioning & conditional loading | inc/enqueue.php: enqueue CSS/JS with filemtime() cache-busting, per-template conditional loading, defer/module attributes, preload primary Arabic font, remove emoji script, no jQuery dependency on the front end. | P0 | Not Started | 2026-10-12 | 2026-10-12 | 0% | P1-02 | Staging (Hostinger) | inc/enqueue.php, assets/css/*, assets/js/* | View source: versioned URLs, deferred scripts; Network tab shows no 404s and no jQuery on homepage | All assets versioned and loaded only where needed; zero console errors |  |  |  | None | Not Tested | 0% | 0% | 1 |  | ✓ Ready | Phase 1¦4 | 46307.0001 |  | Due soon
P1-05 | Phase 1 | PHP Templates | Base template hierarchy | Create header.php, footer.php, index.php, front-page.php, single.php, page.php, archive.php, category.php, tag.php, author.php, search.php, 404.php skeletons sharing a common layout wrapper. | P0 | Not Started | 2026-10-12 | 2026-10-12 | 0% | P1-03 | Staging (Hostinger) | header.php, footer.php, index.php, front-page.php, single.php, page.php, archive.php, category.php, tag.php, author.php, search.php, 404.php | Visit each route type; Query Monitor confirms expected template file | Every WordPress route resolves to a theme template with header/footer; no fallback errors |  |  |  | None | Not Tested | 0% | 0% | 1 |  | ⏳ 1 open | Phase 1¦5 | 46307.0001 |  | Due soon
P1-06 | Phase 1 | Components | Reusable template-part components | template-parts/components: card-hero, card-large, card-medium, card-list, card-mini, section-header, post-meta, category-badge, pagination, ad-slot, empty-state. All accept $args via get_template_part() and escape output (esc_html/esc_url/esc_attr). | P0 | Not Started | 2026-10-12 | 2026-10-12 | 0% | P1-05 | Staging (Hostinger) | template-parts/components/*.php | Render every component on a test page with real posts; test missing image/excerpt; check escaping | Components reused by homepage and archives with no duplicated markup; all output escaped |  |  |  | None | Not Tested | 0% | 0% | 1 |  | ⏳ 1 open | Phase 1¦6 | 46307.0001 |  | Due soon
P1-07 | Phase 1 | CSS Architecture | CSS architecture & design tokens | assets/css: tokens.css (colors, spacing, type scale as custom properties), base, layout, components, utilities, templates. Use CSS logical properties for native RTL. No CSS framework. Minification delegated to LiteSpeed (no local build tooling). | P0 | Not Started | 2026-10-12 | 2026-10-13 | 0% | P1-04 | Staging (Hostinger) | assets/css/tokens.css, base.css, layout.css, components.css, utilities.css | Inspect computed styles use tokens; RTL correct without separate override file; CSS size checked | Single token source; consistent styling; total CSS within agreed budget (target < 100 KB uncompressed) |  |  |  | None | Not Tested | 0% | 0% | 2 |  | ⏳ 1 open | Phase 1¦7 | 46308.0001 |  | Due soon
P1-08 | Phase 1 | Vanilla JS | Vanilla JS module architecture | assets/js/main.js bootstraps data-attribute driven modules (nav, drawer, search overlay, sticky header); IntersectionObserver utilities; respects prefers-reduced-motion; no jQuery. | P0 | Not Started | 2026-10-13 | 2026-10-13 | 0% | P1-04 | Staging (Hostinger) | assets/js/main.js, assets/js/modules/*.js | Console clean on Chrome & Safari; page usable with JS disabled | All interactions implemented in Vanilla JS; zero console errors; scripts deferred |  |  |  | None | Not Tested | 0% | 0% | 2 |  | ⏳ 1 open | Phase 1¦8 | 46308.0001 |  | Due soon
P1-09 | Phase 1 | RTL Typography | RTL layout & Arabic typography | html dir='rtl' lang='ar'; self-hosted Arabic WOFF2 fonts (font-display: swap, subset); Arabic-appropriate line-height & type scale; bidi isolation for mixed Arabic/English strings; numerals policy. | P0 | Not Started | 2026-10-13 | 2026-10-13 | 0% | P1-07 | Staging (Hostinger) | assets/fonts/*, assets/css/base.css, header.php | Headlines/body render in Arabic font on iOS, Android, desktop; no invisible text flash; mixed strings align | Correct RTL direction site-wide; fonts self-hosted; no layout shift from font swap |  |  |  | None | Not Tested | 0% | 0% | 2 |  | ⏳ 1 open | Phase 1¦9 | 46308.0001 |  | Due soon
P1-10 | Phase 1 | Responsive Design | Responsive grid & breakpoints | Mobile-first container and CSS grid; breakpoints 360/576/768/1024/1280+; fluid type with clamp(); responsive images with srcset/sizes. | P0 | Not Started | 2026-10-13 | 2026-10-13 | 0% | P1-07 | Staging (Hostinger) | assets/css/layout.css | Test 360, 414, 768, 1024, 1440 px widths; no horizontal scroll | All layouts usable at 360 px; no overflow; correctly sized images |  |  |  | None | Not Tested | 0% | 0% | 2 |  | ⏳ 1 open | Phase 1¦10 | 46308.0001 |  | Due soon
P1-11 | Phase 1 | Header & Navigation | Header, navigation, mobile drawer & search | Top bar with Arabic date, custom logo, primary menu with dropdowns, off-canvas mobile drawer, search overlay, sticky header; keyboard and screen-reader accessible. | P0 | Not Started | 2026-10-13 | 2026-10-14 | 0% | P1-06, P1-08, P1-15 | Staging (Hostinger) | header.php, template-parts/header/*.php, assets/js/modules/nav.js | Drawer opens/closes, Esc closes, focus trapped; search submits; menu edited in WP admin updates header | Navigation works on touch and keyboard; fully managed from WordPress menus |  |  |  | None | Not Tested | 0% | 0% | 3 |  | ⏳ 3 open | Phase 1¦11 | 46309.0002 |  | On track
P1-12 | Phase 1 | Footer | Footer with editable menus & social links | Footer menus, social links via Customizer, newsletter/CTA slot, copyright, back-to-top. | P1 | Not Started | 2026-10-14 | 2026-10-14 | 0% | P1-06 | Staging (Hostinger) | footer.php, template-parts/footer/*.php | All links resolve; social URLs editable in Customizer | Footer content editable without code |  |  |  | None | Not Tested | 0% | 0% | 3 |  | ⏳ 1 open | Phase 1¦12 | 46309.0002 |  | On track
P1-13 | Phase 1 | WordPress Integration | Core WordPress integration & editor styles | wp_head/wp_body_open/wp_footer, body_class/post_class, widget areas (article sidebar, archive sidebar, footer), skip-link, editor-style.css so Gutenberg preview matches front end, oEmbed styling. | P0 | Not Started | 2026-10-14 | 2026-10-14 | 0% | P1-05 | Staging (Hostinger) | functions.php, inc/widgets.php, assets/css/editor-style.css | SEO and LiteSpeed plugins inject head tags; widgets render; editor preview matches front end | Theme compatible with WordPress core and active plugins; no missing hooks |  |  |  | None | Not Tested | 0% | 0% | 3 |  | ⏳ 1 open | Phase 1¦13 | 46309.0002 |  | On track
P1-14 | Phase 1 | Query Caching | Query caching layer with auto-invalidation | inc/cache.php: altijara_cached_query($key,$args,$ttl) using transients/object cache with versioned namespaced keys; invalidation on save_post, transition_post_status, delete_post and term edits; no_found_rows/fields optimizations. | P0 | Not Started | 2026-10-14 | 2026-10-14 | 0% | P1-03 | Staging (Hostinger) | inc/cache.php | Query Monitor shows reduced queries on warm load; publishing a post refreshes affected sections immediately | Homepage warm-cache DB queries within target (≤ 40); no stale content after publish |  |  |  | None | Not Tested | 0% | 0% | 3 |  | ⏳ 1 open | Phase 1¦14 | 46309.0002 |  | On track
P1-15 | Phase 1 | Date Helpers | Arabic date, relative time & reading-time helpers | inc/helpers-date.php: Arabic month/day names, formatted dates, relative time (e.g. 'منذ ساعتين'), optional Arabic-Indic digits, Hijri date for top bar if required, reading-time estimator. | P1 | Not Started | 2026-10-14 | 2026-10-14 | 0% | P1-03 | Staging (Hostinger) | inc/helpers-date.php | Check outputs for today, yesterday, last month and last year in site timezone | All templates use helpers; dates correct in site timezone |  |  |  | None | Not Tested | 0% | 0% | 3 |  | ⏳ 1 open | Phase 1¦15 | 46309.0002 |  | On track
P1-16 | Phase 1 | Media | Image handling, lazy-load & fallbacks | Lazy-loading, srcset/sizes on every card, default fallback image for legacy posts without thumbnails, WebP via LiteSpeed/hosting, aspect-ratio boxes to prevent CLS. | P1 | Not Started | 2026-10-14 | 2026-10-14 | 0% | P1-06 | Staging (Hostinger) | inc/media.php, template-parts/components/* | Legacy post without featured image shows fallback; no layout shift on card grids | Every card shows an image or fallback; CLS < 0.1 on archives |  |  |  | None | Not Tested | 0% | 0% | 3 |  | ⏳ 1 open | Phase 1¦16 | 46309.0002 |  | On track
P1-17 | Phase 1 | Phase QA | Phase 1 verification & tag v0.1 | Activate theme on staging, review debug.log, PHP 8.x compatibility, render sample pages, tag release v0.1 in Git. | P0 | Not Started | 2026-10-14 | 2026-10-14 | 0% | P1-11, P1-13, P1-14, P1-16 | Staging (Hostinger) | debug.log | debug.log has no theme notices; all templates load | Foundation signed off; Phase 2 can start |  |  |  | None | Not Tested | 0% | 0% | 3 |  | ⏳ 4 open | Phase 1¦17 | 46309.0002 |  | On track
P2-01 | Phase 2 | Section Manager | Section Manager engine & schema | inc/section-manager/: registry where each section defines title, source type (category / tag / manual), term IDs, post count, orderby, order, offset, exclude-duplicates, layout, visibility, cache TTL, ad slot; renderer maps sections to components. | P0 | Not Started | 2026-10-15 | 2026-10-15 | 0% | P1-06, P1-14 | Staging (Hostinger) | inc/section-manager/registry.php, query-builder.php, render.php | Register a test section; change schema values; output changes accordingly | Every homepage section is rendered from the registry; no hard-coded queries in front-page.php |  |  |  | None | Not Tested | 0% | 0% | 4 |  | ⏳ 2 open | Phase 2¦1 | 46310.0002 |  | On track
P2-02 | Phase 2 | Customizer | Customizer 'Homepage Sections' panel | Panel with one section per homepage block; settings stored as theme_mods; sanitize callback on every control; selective refresh / postMessage preview where possible. | P0 | Not Started | 2026-10-15 | 2026-10-15 | 0% | P2-01 | Staging (Hostinger) | inc/customizer/panel-homepage.php, assets/js/customizer-preview.js | Editor (non-admin) changes a section in Customizer and publishes; invalid values rejected | All sections configurable in Customizer with live preview and sanitized values |  |  |  | None | Not Tested | 0% | 0% | 4 |  | ⏳ 1 open | Phase 2¦2 | 46310.0002 |  | On track
P2-03 | Phase 2 | Customizer Controls | Dynamic category / tag selection | Custom WP_Customize_Control: searchable multi-select for categories and tags storing term IDs (survives renames). | P0 | Not Started | 2026-10-15 | 2026-10-15 | 0% | P2-02 | Staging (Hostinger) | inc/customizer/controls/term-select.php, assets/js/customizer-controls.js | Select 2 categories + 1 tag; rename a category; section still pulls correctly | Sections can be sourced from any category/tag combination by ID |  |  |  | None | Not Tested | 0% | 0% | 4 |  | ⏳ 1 open | Phase 2¦3 | 46310.0002 |  | On track
P2-04 | Phase 2 | Customizer Controls | Post count, sorting & offset controls | Count (1–20), orderby (date, modified, comment_count, most-read, random), order ASC/DESC and offset; query builder maps to WP_Query args. | P0 | Not Started | 2026-10-15 | 2026-10-15 | 0% | P2-03 | Staging (Hostinger) | inc/section-manager/query-builder.php | Change count, order and offset; verify returned posts in Query Monitor | Count, sorting and offset behave exactly as configured |  |  |  | None | Not Tested | 0% | 0% | 4 |  | ⏳ 1 open | Phase 2¦4 | 46310.0003 |  | On track
P2-05 | Phase 2 | Customizer Controls | Manual post selection (post picker) | Post-picker control searching /wp/v2/posts via REST with sortable selected list; manual selection overrides automatic source. | P1 | Not Started | 2026-10-15 | 2026-10-15 | 0% | P2-02 | Staging (Hostinger) | inc/customizer/controls/post-picker.php, assets/js/customizer-controls.js | Pick 4 posts, reorder, publish; homepage shows them in chosen order | Editors can pin specific posts in a chosen order |  |  |  | None | Not Tested | 0% | 0% | 4 |  | ⏳ 1 open | Phase 2¦5 | 46310.0003 |  | On track
P2-06 | Phase 2 | Customizer Controls | Layout switching per section | Layout variants per section (hero+list, grid-3, grid-4, list, slider, carousel) mapped to component templates. | P1 | Not Started | 2026-10-15 | 2026-10-15 | 0% | P2-01 | Staging (Hostinger) | template-parts/sections/*.php | Switch each section through every layout at 360 px and 1440 px | Each layout renders correctly and responsively |  |  |  | None | Not Tested | 0% | 0% | 4 |  | ⏳ 1 open | Phase 2¦6 | 46310.0003 |  | On track
P2-07 | Phase 2 | Customizer Controls | Section visibility, ordering & de-duplication | Show/hide toggle per section, sortable section order setting, global de-duplication so a post appears only once on the homepage. | P0 | Not Started | 2026-10-15 | 2026-10-16 | 0% | P2-02 | Staging (Hostinger) | inc/section-manager/render.php, inc/customizer/controls/sortable.php | Hide a section, reorder two sections, confirm no duplicate posts across sections | Visibility, order and de-duplication controlled from Customizer |  |  |  | None | Not Tested | 0% | 0% | 5 |  | ⏳ 1 open | Phase 2¦7 | 46311.0003 |  | On track
P2-08 | Phase 2 | Cache Controls | Section cache controls + LiteSpeed purge | Per-section TTL; 'Purge homepage cache' button (nonce + capability check); auto-purge on publish/update; triggers LiteSpeed purge action. | P0 | Not Started | 2026-10-16 | 2026-10-16 | 0% | P1-14, P2-01 | Staging (Hostinger) | inc/section-manager/cache.php | Publish a post → appears on homepage after purge; purge button works only for editors+ | Homepage never serves stale sections after publish; manual purge available |  |  |  | None | Not Tested | 0% | 0% | 5 |  | ⏳ 2 open | Phase 2¦8 | 46311.0003 |  | On track
P2-09 | Phase 2 | Homepage Sections | Homepage hero | Lead story + 2–4 secondary stories sourced via Section Manager (featured tag or manual picks), responsive art direction. | P0 | Not Started | 2026-10-16 | 2026-10-16 | 0% | P2-01 | Staging (Hostinger) | template-parts/sections/hero.php | Change hero source; check mobile crop and title wrapping in Arabic | Hero is editor-controlled and renders well on all breakpoints |  |  |  | None | Not Tested | 0% | 0% | 5 |  | ⏳ 1 open | Phase 2¦9 | 46311.0003 |  | On track
P2-10 | Phase 2 | Homepage Sections | Breaking news ticker | Source tag/category (e.g. 'عاجل'); Vanilla JS RTL marquee; pause on hover/focus; reduced-motion fallback; hidden when empty. | P0 | Not Started | 2026-10-16 | 2026-10-16 | 0% | P2-01 | Staging (Hostinger) | template-parts/sections/ticker.php, assets/js/modules/ticker.js | Add/remove breaking tag; test RTL scroll direction, hover pause, reduced motion | Ticker updates from WordPress, scrolls RTL and is accessible |  |  |  | None | Not Tested | 0% | 0% | 5 |  | ⏳ 1 open | Phase 2¦10 | 46311.0003 |  | On track
P2-11 | Phase 2 | Homepage Sections | Magazine cover slider | Latest N issues from magazine_issue CPT; touch swipe; lazy covers; links to single issue. Built with placeholders, wired once CPT exists. | P1 | Not Started | 2026-10-16 | 2026-10-16 | 0% | P2-01, P4-01 | Staging (Hostinger) | template-parts/sections/cover-slider.php, assets/js/modules/slider.js | Swipe on mobile; covers lazy-load; links open correct issue | Slider shows latest issues automatically |  |  |  | None | Not Tested | 0% | 0% | 5 |  | ⏳ 2 open | Phase 2¦11 | 46311.0003 |  | On track
P2-12 | Phase 2 | Homepage Sections | Chamber section | Chamber news block with configurable source and layout. | P1 | Not Started | 2026-10-16 | 2026-10-16 | 0% | P2-01 | Staging (Hostinger) | template-parts/sections/* | Configure source and layout; verify output | Chamber section renders configured posts |  |  |  | None | Not Tested | 0% | 0% | 5 |  | ⏳ 1 open | Phase 2¦12 | 46311.0003 |  | On track
P2-13 | Phase 2 | Homepage Sections | Opinion / columnists section | Columnist cards with author avatar, name and column title; links to author profiles. | P1 | Not Started | 2026-10-16 | 2026-10-16 | 0% | P2-01 | Staging (Hostinger) | template-parts/sections/opinion.php | Check avatars, author links, fallback avatar | Opinion section shows writers with working profile links |  |  |  | None | Not Tested | 0% | 0% | 5 |  | ⏳ 1 open | Phase 2¦13 | 46311.0004 |  | On track
P2-14 | Phase 2 | Homepage Sections | Reports section | Reports block with featured report + list layout. | P1 | Not Started | 2026-10-16 | 2026-10-17 | 0% | P2-01 | Staging (Hostinger) | template-parts/sections/* | Configure; verify output and layout | Reports section renders configured posts |  |  |  | None | Not Tested | 0% | 0% | 6 |  | ⏳ 1 open | Phase 2¦14 | 46312.0004 |  | On track
P2-15 | Phase 2 | Homepage Sections | Latest news & article grid sections | Generic article grids (latest news, more stories) with 'view all' link to archive. | P0 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-01 | Staging (Hostinger) | template-parts/sections/grid.php | Verify counts, links and de-duplication | Article grids render and link to archives |  |  |  | None | Not Tested | 0% | 0% | 6 |  | ⏳ 1 open | Phase 2¦15 | 46312.0004 |  | On track
P2-16 | Phase 2 | Sector Sections | Business section | Configure and style Business section via Section Manager. | P1 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-15 | Staging (Hostinger) | template-parts/sections/* | Verify source, count, layout | Section live and editor-configurable |  |  |  | None | Not Tested | 0% | 0% | 6 |  | ⏳ 1 open | Phase 2¦16 | 46312.0004 |  | On track
P2-17 | Phase 2 | Sector Sections | Real Estate section | Configure and style Real Estate section via Section Manager. | P1 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-15 | Staging (Hostinger) | template-parts/sections/* | Verify source, count, layout | Section live and editor-configurable |  |  |  | None | Not Tested | 0% | 0% | 6 |  | ⏳ 1 open | Phase 2¦17 | 46312.0004 |  | On track
P2-18 | Phase 2 | Sector Sections | Automotive section | Configure and style Automotive section via Section Manager. | P1 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-15 | Staging (Hostinger) | template-parts/sections/* | Verify source, count, layout | Section live and editor-configurable |  |  |  | None | Not Tested | 0% | 0% | 6 |  | ⏳ 1 open | Phase 2¦18 | 46312.0004 |  | On track
P2-19 | Phase 2 | Sector Sections | Technology section | Configure and style Technology section via Section Manager. | P1 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-15 | Staging (Hostinger) | template-parts/sections/* | Verify source, count, layout | Section live and editor-configurable |  |  |  | None | Not Tested | 0% | 0% | 6 |  | ⏳ 1 open | Phase 2¦19 | 46312.0004 |  | On track
P2-20 | Phase 2 | Sector Sections | Healthcare section | Configure and style Healthcare section via Section Manager. | P1 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-15 | Staging (Hostinger) | template-parts/sections/* | Verify source, count, layout | Section live and editor-configurable |  |  |  | None | Not Tested | 0% | 0% | 6 |  | ⏳ 1 open | Phase 2¦20 | 46312.0004 |  | On track
P2-21 | Phase 2 | Sector Sections | Tourism section | Configure and style Tourism section via Section Manager. | P1 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-15 | Staging (Hostinger) | template-parts/sections/* | Verify source, count, layout | Section live and editor-configurable |  |  |  | None | Not Tested | 0% | 0% | 6 |  | ⏳ 1 open | Phase 2¦21 | 46312.0004 |  | On track
P2-22 | Phase 2 | Most Read | Most-read widget & view counter | Reuse legacy JNews view meta if present (see P6-04), else lightweight counter via REST beacon (works behind page cache) with bot filtering & throttling; 24h/7d/30d tabs; cached; usable as widget and homepage block. | P0 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P1-14, P6-04 | Staging (Hostinger) | inc/most-read.php, inc/widgets/most-read-widget.php, assets/js/modules/views.js | Open articles in private windows; counts increase once per session; tabs switch | Most-read list accurate, cached, and works with LiteSpeed page cache |  |  |  | None | Not Tested | 0% | 0% | 6 |  | ⏳ 2 open | Phase 2¦22 | 46312.0004 |  | On track
P2-23 | Phase 2 | AdOps | Homepage advertisement slots | Leaderboard/MPU slots between sections managed via Customizer/widgets (image+link or ad code), lazy-loaded, reserved space to avoid CLS. | P1 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-01 | Staging (Hostinger) | template-parts/components/ad-slot.php | Add an ad in Customizer; check placement & no layout shift | Ads managed without code; no CLS |  |  |  | None | Not Tested | 0% | 0% | 6 |  | ⏳ 1 open | Phase 2¦23 | 46312.0004 |  | On track
P2-24 | Phase 2 | Phase QA | Homepage performance & responsive sign-off | Query Monitor (queries/time), Lighthouse mobile, RTL/responsive pass; share staging link with client for feedback. | P0 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-09, P2-10, P2-22 | Staging (Hostinger) | front-page.php | Lighthouse mobile run; Query Monitor warm/cold; 360/768/1440 check | Homepage meets performance targets and is approved for Phase 3 |  |  |  | None | Not Tested | 0% | 0% | 6 |  | ⏳ 3 open | Phase 2¦24 | 46312.0005 |  | On track
P3-01 | Phase 3 | Single Article | Single article template | single.php: headline, subtitle/excerpt, featured image with caption & credit, content typography, tags, author box, sidebar (most-read, ads). | P0 | Not Started | 2026-10-18 | 2026-10-18 | 0% | P1-17 | Staging (Hostinger) | single.php, template-parts/article/*.php | Open 20 sample articles across years and categories | Articles render correctly with full layout on all breakpoints |  |  |  | None | Not Tested | 0% | 0% | 7 |  | ⏳ 1 open | Phase 3¦1 | 46313.0005 |  | On track
P3-02 | Phase 3 | Article Metadata | Article metadata | Author, publish & updated dates (Arabic helpers), reading time, category badges, tags, view count. | P0 | Not Started | 2026-10-18 | 2026-10-18 | 0% | P3-01, P1-15 | Staging (Hostinger) | template-parts/article/meta.php | Compare metadata with WP admin values for 10 posts | Metadata accurate and localized |  |  |  | None | Not Tested | 0% | 0% | 7 |  | ⏳ 2 open | Phase 3¦2 | 46313.0005 |  | On track
P3-03 | Phase 3 | Legacy Content | Legacy JNews content & shortcode rendering | Render or gracefully strip JNews shortcodes/legacy markup found in the audit; style classic & Gutenberg content (images, captions, galleries, embeds, tables, blockquotes). | P0 | Not Started | 2026-10-18 | 2026-10-18 | 0% | P3-01, P6-04 | Staging (Hostinger) | inc/legacy-shortcodes.php, assets/css/content.css | Open posts flagged in P6-04 audit; no raw [shortcodes] visible | No raw shortcodes or broken legacy markup in any of the 2,645 articles |  |  |  | None | Not Tested | 0% | 0% | 7 |  | ⏳ 2 open | Phase 3¦3 | 46313.0005 |  | On track
P3-04 | Phase 3 | Engagement | Reading progress bar | Vanilla JS progress indicator (requestAnimationFrame), RTL fill direction, hidden on short posts. | P1 | Not Started | 2026-10-18 | 2026-10-18 | 0% | P3-01 | Staging (Hostinger) | assets/js/modules/progress.js | Scroll long article; check direction and smoothness on mobile | Progress bar accurate, smooth, RTL |  |  |  | None | Not Tested | 0% | 0% | 7 |  | ⏳ 1 open | Phase 3¦4 | 46313.0005 |  | On track
P3-05 | Phase 3 | Engagement | Social sharing | WhatsApp, X, Facebook, LinkedIn, Telegram, copy-link and native Web Share API on mobile; no third-party scripts. | P1 | Not Started | 2026-10-18 | 2026-10-18 | 0% | P3-01 | Staging (Hostinger) | template-parts/article/share.php, assets/js/modules/share.js | Share each network; check URL encoding of Arabic titles | All share targets open with correct title and URL |  |  |  | None | Not Tested | 0% | 0% | 7 |  | ⏳ 1 open | Phase 3¦5 | 46313.0005 |  | On track
P3-06 | Phase 3 | AdOps | In-article advertisement injection | the_content filter injects ad slot after paragraph N and every M paragraphs; skips short articles; never inside blockquote/table/embed; configurable in Customizer. | P1 | Not Started | 2026-10-18 | 2026-10-19 | 0% | P3-01, P2-23 | Staging (Hostinger) | inc/content-filters.php | Test short, long and embed-heavy articles | Ads appear at configured positions without breaking content |  |  |  | None | Not Tested | 0% | 0% | 8 |  | ⏳ 2 open | Phase 3¦6 | 46314.0005 |  | On track
P3-07 | Phase 3 | Engagement | Related articles | Related posts by shared category + tags, cached, excludes current post, fallback to latest in category. | P1 | Not Started | 2026-10-19 | 2026-10-19 | 0% | P3-01, P1-14 | Staging (Hostinger) | template-parts/article/related.php | Check relevance on 5 posts; check cache | Related list relevant and cached |  |  |  | None | Not Tested | 0% | 0% | 8 |  | ⏳ 2 open | Phase 3¦7 | 46314.0005 |  | On track
P3-08 | Phase 3 | Author Profiles | Author box & author profile template | Author box on articles; author.php with avatar, bio, social links, role and paginated post list. | P0 | Not Started | 2026-10-19 | 2026-10-19 | 0% | P1-06 | Staging (Hostinger) | author.php, template-parts/article/author-box.php | Open 5 author pages incl. one with no bio/avatar | Every author has a working profile page |  |  |  | None | Not Tested | 0% | 0% | 8 |  | ⏳ 1 open | Phase 3¦8 | 46314.0005 |  | On track
P3-09 | Phase 3 | Category Archives | Category archive template | category.php with category hero, featured lead post, subcategory navigation, post grid, sidebar. | P0 | Not Started | 2026-10-19 | 2026-10-19 | 0% | P1-06 | Staging (Hostinger) | category.php, archive.php | Check every top-level category and 3 subcategories | All categories render with correct posts and SEO-friendly URLs |  |  |  | None | Not Tested | 0% | 0% | 8 |  | ⏳ 1 open | Phase 3¦9 | 46314.0005 |  | On track
P3-10 | Phase 3 | Taxonomy | Tag archive, search results & 404 | tag.php, search.php with highlighted results, 404.php with search and latest posts. | P1 | Not Started | 2026-10-19 | 2026-10-19 | 0% | P3-09 | Staging (Hostinger) | tag.php, search.php, 404.php | Search Arabic terms; visit unknown URL | Search returns relevant results; 404 helpful |  |  |  | None | Not Tested | 0% | 0% | 8 |  | ⏳ 1 open | Phase 3¦10 | 46314.0006 |  | On track
P3-11 | Phase 3 | AJAX Filtering | AJAX archive filtering | REST endpoint (nonce, sanitized params) filtering by subcategory, date range and sort; updates grid without reload; history.pushState with crawlable fallback URLs. | P1 | Not Started | 2026-10-19 | 2026-10-20 | 0% | P3-09 | Staging (Hostinger) | inc/rest/archive-filter.php, assets/js/modules/filter.js | Apply filters; use back button; disable JS and confirm links still work | Filtering fast (< 500 ms server), shareable URLs, works without JS |  |  |  | None | Not Tested | 0% | 0% | 9 |  | ⏳ 1 open | Phase 3¦11 | 46315.0006 |  | On track
P3-12 | Phase 3 | Archive UX | Grid / list view switching | Toggle between grid and list views; remembers preference per visitor. | P2 | Not Started | 2026-10-20 | 2026-10-20 | 0% | P3-09 | Staging (Hostinger) | assets/js/modules/view-toggle.js | Toggle on archive; reload page; preference kept | Toggle works on all archives |  |  |  | None | Not Tested | 0% | 0% | 9 |  | ⏳ 1 open | Phase 3¦12 | 46315.0006 |  | On track
P3-13 | Phase 3 | Pagination | Pagination | Numbered pagination with SEO-friendly /page/N/ URLs; optional 'load more' enhancement. | P0 | Not Started | 2026-10-20 | 2026-10-20 | 0% | P3-09 | Staging (Hostinger) | template-parts/components/pagination.php | Navigate to last page of large category; check rel/canonical | Pagination works on all archives without duplicate content issues |  |  |  | None | Not Tested | 0% | 0% | 9 |  | ⏳ 1 open | Phase 3¦13 | 46315.0006 |  | On track
P3-14 | Phase 3 | Print | Print stylesheet | print.css hiding nav/ads/share, readable article typography, URL and date in footer. | P2 | Not Started | 2026-10-20 | 2026-10-20 | 0% | P3-01 | Staging (Hostinger) | assets/css/print.css | Print preview article in Chrome and Safari | Clean printable article |  |  |  | None | Not Tested | 0% | 0% | 9 |  | ⏳ 1 open | Phase 3¦14 | 46315.0006 |  | On track
P3-15 | Phase 3 | SEO | SEO compatibility, schema & breadcrumbs | Compatibility with the active SEO plugin (titles, meta, canonical, OG/Twitter, sitemaps); NewsArticle/Article schema; breadcrumbs; no duplicate meta from theme. | P0 | Not Started | 2026-10-20 | 2026-10-20 | 0% | P3-01, P3-09, P6-06 | Staging (Hostinger) | inc/seo.php, header.php | Compare head tags with baseline; Rich Results test on 3 articles | SEO output matches or improves baseline; valid structured data |  |  |  | None | Not Tested | 0% | 0% | 9 |  | ⏳ 3 open | Phase 3¦15 | 46315.0006 |  | On track
P3-16 | Phase 3 | Phase QA | Editorial templates sign-off | Run template checks from QA sheet for article, category, author, tag and search templates. | P0 | Not Started | 2026-10-20 | 2026-10-20 | 0% | P3-03, P3-11, P3-15 | Staging (Hostinger) | — | QA sheet rows for templates 2–4 | Templates approved for Phase 4 |  |  |  | None | Not Tested | 0% | 0% | 9 |  | ⏳ 3 open | Phase 3¦16 | 46315.0006 |  | On track
P4-01 | Phase 4 | CPT Engine | Register magazine_issue custom post type | inc/cpt-issues.php: CPT with archive, rewrite slug, REST support, labels in Arabic, supports title/thumbnail/excerpt. | P0 | Not Started | 2026-10-21 | 2026-10-21 | 0% | P1-17 | Staging (Hostinger) | inc/cpt-issues.php | Create test issue; check archive URL and REST response; flush permalinks | CPT live with clean URLs |  |  |  | None | Not Tested | 0% | 0% | 10 |  | ⏳ 1 open | Phase 4¦1 | 46316.0006 |  | On track
P4-02 | Phase 4 | CPT Engine | Issue fields: number, date, year, decade, PDF, access | Meta fields: issue number, publication month/year, year & decade (auto-derived), PDF attachment, page count, access level (free / members / subscribers), featured articles. | P0 | Not Started | 2026-10-21 | 2026-10-21 | 0% | P4-01 | Staging (Hostinger) | inc/issue-meta.php | Save issue; decade auto-calculates; invalid values rejected | All issue metadata editable and validated |  |  |  | None | Not Tested | 0% | 0% | 10 |  | ⏳ 1 open | Phase 4¦2 | 46316.0006 |  | On track
P4-03 | Phase 4 | Historical Assets | Collect 48 historical issue PDFs, covers & manifest | Request from client: all 48 PDFs, cover images and a manifest (issue number, date, title). Track missing items. | P0 | Not Started | 2026-10-12 | 2026-10-20 | 0% |  | External / Third-party | url: shared drive | Count received files = 48 PDFs + 48 covers; manifest complete | All historical assets received and checked |  |  |  | Historical Assets | Not Tested | 0% | 0% | 9 |  |  | Phase 4¦3 | 46315.0007 |  | External req.
P4-04 | Phase 4 | Migration | Historical issue migration (import 48 issues) | CSV manifest + idempotent importer (WP-CLI via Hostinger SSH or one-time admin tool) creating issues, attaching covers and PDFs; re-runnable without duplicates. | P0 | Not Started | 2026-10-21 | 2026-10-21 | 0% | P4-02, P4-03 | Staging (Hostinger) | inc/issue-import.php, issues-manifest.csv | Run import twice; still 48 issues; spot-check 10 | All 48 issues imported with correct metadata, covers and PDFs |  |  |  | Server Access | Not Tested | 0% | 0% | 10 |  | ⏳ 2 open | Phase 4¦4 | 46316.0007 |  | External req.
P4-05 | Phase 4 | Cover Images | Cover image optimization | Generate WebP and required sizes for covers; consistent aspect ratio. | P1 | Not Started | 2026-10-21 | 2026-10-21 | 0% | P4-04 | Staging (Hostinger) | inc/media.php | Check archive weight and image dimensions | Covers sharp and lightweight |  |  |  | None | Not Tested | 0% | 0% | 10 |  | ⏳ 1 open | Phase 4¦5 | 46316.0007 |  | On track
P4-06 | Phase 4 | Issue Archive | Issue archive template | archive-magazine_issue.php: cover grid, newest first, issue number/date, pagination. | P0 | Not Started | 2026-10-21 | 2026-10-21 | 0% | P4-01 | Staging (Hostinger) | archive-magazine_issue.php, template-parts/issue/card.php | Open archive; check ordering and pagination | Archive lists all issues correctly |  |  |  | None | Not Tested | 0% | 0% | 10 |  | ⏳ 1 open | Phase 4¦6 | 46316.0007 |  | On track
P4-07 | Phase 4 | Issue Archive | Year & decade filtering | Filter issues by decade then year (query vars + optional AJAX), crawlable URLs. | P1 | Not Started | 2026-10-21 | 2026-10-21 | 0% | P4-06 | Staging (Hostinger) | archive-magazine_issue.php, assets/js/modules/issue-filter.js | Filter each decade/year; counts match manifest | Filters return correct issues |  |  |  | None | Not Tested | 0% | 0% | 10 |  | ⏳ 1 open | Phase 4¦7 | 46316.0007 |  | On track
P4-08 | Phase 4 | Single Issue | Single issue page | single-magazine_issue.php: large cover, issue details, highlights/table of contents, read & download actions, previous/next issue. | P0 | Not Started | 2026-10-22 | 2026-10-22 | 0% | P4-02 | Staging (Hostinger) | single-magazine_issue.php | Open 5 issues incl. oldest and newest | Single issue page complete for every issue |  |  |  | None | Not Tested | 0% | 0% | 11 |  | ⏳ 1 open | Phase 4¦8 | 46317.0007 |  | On track
P4-09 | Phase 4 | Flipbook | Flipbook reader | Self-hosted PDF.js based flipbook, lazy-loaded only on issue pages, page navigation, zoom, fullscreen; mobile fallback to scroll view. | P1 | Not Started | 2026-10-22 | 2026-10-22 | 0% | P4-08 | Staging (Hostinger) | assets/js/modules/flipbook.js, assets/vendor/pdfjs/* | Open large PDF on mobile & desktop; measure load time | Readable flipbook on desktop & mobile without blocking page load |  |  |  | None | Not Tested | 0% | 0% | 11 |  | ⏳ 1 open | Phase 4¦9 | 46317.0007 |  | On track
P4-10 | Phase 4 | PDF Downloads | Secure PDF downloads | Download endpoint with nonce and access check, download counter, correct filename/headers. | P0 | Not Started | 2026-10-22 | 2026-10-22 | 0% | P4-08 | Staging (Hostinger) | inc/pdf-download.php | Download as guest/member/subscriber; check headers | Downloads work and respect access rules |  |  |  | None | Not Tested | 0% | 0% | 11 |  | ⏳ 1 open | Phase 4¦10 | 46317.0007 |  | On track
P4-11 | Phase 4 | Access Control | Issue access restrictions | Gate reader and downloads by access level/subscription tier; block direct /uploads PDF access (.htaccess/LiteSpeed rule) or serve via PHP. | P0 | Not Started | 2026-10-22 | 2026-10-22 | 0% | P4-10, P5-07 | Staging (Hostinger) | inc/pdf-download.php, .htaccess | Try direct PDF URL logged-out; test each tier | Restricted PDFs cannot be accessed without entitlement |  |  |  | Server Access | Not Tested | 0% | 0% | 11 |  | ⏳ 2 open | Phase 4¦11 | 46317.0007 |  | External req.
P4-12 | Phase 4 | Phase QA | Verify all 48 issues | Checklist pass: 48/48 issues present, cover, PDF opens, metadata correct, filters accurate. | P0 | Not Started | 2026-10-22 | 2026-10-22 | 0% | P4-04, P4-07, P4-09 | Staging (Hostinger) | issues-manifest.csv | Tick all 48 against manifest | 48/48 issues verified |  |  |  | None | Not Tested | 0% | 0% | 11 |  | ⏳ 3 open | Phase 4¦12 | 46317.0007 |  | On track
P5-01 | Phase 5 | Credentials | Request Google OAuth credentials | Google Cloud project, OAuth consent screen, client ID/secret, authorised redirect URIs for staging and production. | P1 | Not Started | 2026-10-12 | 2026-10-20 | 0% |  | External / Third-party | — | Credentials received and stored securely (not in Git) | Valid client ID/secret for both domains |  |  |  | Credentials | Not Tested | 0% | 0% | 9 |  |  | Phase 5¦1 | 46315.0007 |  | External req.
P5-02 | Phase 5 | Credentials | Request Sign in with Apple credentials | Apple Developer Program membership (client), Services ID, key, team ID, domain verification for both domains. | P1 | Not Started | 2026-10-12 | 2026-10-20 | 0% |  | External / Third-party | — | Credentials received; domain verification file placed | Valid Apple credentials for both domains |  |  |  | Credentials | Not Tested | 0% | 0% | 9 |  |  | Phase 5¦2 | 46315.0008 |  | External req.
P5-03 | Phase 5 | Payments | Confirm payment provider & obtain API keys | Client confirms gateway; obtain sandbox + live API keys, webhook signing secret, merchant approval and supported currencies. | P0 | Not Started | 2026-10-12 | 2026-10-22 | 0% |  | External / Third-party | — | Sandbox transaction possible; live approval date known | Sandbox keys in hand; live approval confirmed before cutover |  |  |  | Payment Approval | Not Tested | 0% | 0% | 11 |  |  | Phase 5¦3 | 46317.0008 |  | External req.
P5-04 | Phase 5 | Authentication | Login, registration & password reset | Custom templates using wp_signon/wp_insert_user; email verification; password reset flow; redirects; Arabic validation messages; wp-login.php styled fallback. | P0 | Not Started | 2026-10-23 | 2026-10-23 | 0% | P1-17 | Staging (Hostinger) | page-templates/page-login.php, page-register.php, page-reset.php, inc/auth/*.php | Register, verify, log in, reset password, log out | Complete account lifecycle works with clear Arabic messages |  |  |  | None | Not Tested | 0% | 0% | 12 |  | ⏳ 1 open | Phase 5¦4 | 46318.0008 |  | On track
P5-05 | Phase 5 | Authentication | Google sign-in | OAuth 2.0 flow (state param, token verification), link to existing account by verified email. | P1 | Not Started | 2026-10-23 | 2026-10-23 | 0% | P5-01, P5-04 | Staging (Hostinger) | inc/auth/social-google.php | New and existing user sign-in; cancel flow | Google sign-in works on staging and is ready for production URIs |  |  |  | Credentials | Not Tested | 0% | 0% | 12 |  | ⏳ 2 open | Phase 5¦5 | 46318.0008 |  | External req.
P5-06 | Phase 5 | Authentication | Sign in with Apple | Apple JS/redirect flow, JWT verification, private-relay email handling, account linking. | P2 | Not Started | 2026-10-23 | 2026-10-23 | 0% | P5-02, P5-04 | Staging (Hostinger) | inc/auth/social-apple.php | Sign in on Safari iOS & desktop; hide-my-email case | Apple sign-in works including private relay emails |  |  |  | Credentials | Not Tested | 0% | 0% | 12 |  | ⏳ 2 open | Phase 5¦6 | 46318.0008 |  | External req.
P5-07 | Phase 5 | Subscriptions | Subscription tiers model | Tiers (e.g. Free, Digital, Premium) via roles/capabilities + user meta (plan, start, expiry); tier config editable in admin; pricing page. | P0 | Not Started | 2026-10-23 | 2026-10-23 | 0% | P5-04 | Staging (Hostinger) | inc/subscriptions/tiers.php, page-templates/page-subscribe.php | Assign each tier manually; check entitlements | Tiers control access across issues and content |  |  |  | None | Not Tested | 0% | 0% | 12 |  | ⏳ 1 open | Phase 5¦7 | 46318.0008 |  | On track
P5-08 | Phase 5 | Payments | Payment gateway checkout integration | Hosted checkout (sandbox first), order record, success/failure pages, currency handling; no card data touches the server. | P0 | Not Started | 2026-10-23 | 2026-10-24 | 0% | P5-03, P5-07 | Staging (Hostinger) | inc/payments/gateway.php | Sandbox: success, decline, cancel | Paid checkout activates correct tier in sandbox |  |  |  | Payment Approval | Not Tested | 0% | 0% | 13 |  | ⏳ 2 open | Phase 5¦8 | 46319.0008 |  | External req.
P5-09 | Phase 5 | Payments | Payment webhooks | Webhook endpoint with signature verification, idempotency keys, event logging, status transitions (paid, failed, refunded, renewed). | P0 | Not Started | 2026-10-24 | 2026-10-24 | 0% | P5-08 | Staging (Hostinger) | inc/payments/webhook.php | Replay same event twice; tampered signature rejected | Subscription state always matches gateway; duplicates ignored |  |  |  | Payment Approval | Not Tested | 0% | 0% | 13 |  | ⏳ 1 open | Phase 5¦9 | 46319.0008 |  | External req.
P5-10 | Phase 5 | Subscriptions | Renewal, expiry & notification emails | Daily cron for expiry, grace period, renewal reminders and receipts. | P1 | Not Started | 2026-10-24 | 2026-10-24 | 0% | P5-09, P5-13 | Staging (Hostinger) | inc/subscriptions/cron.php | Force-expire a test user; check emails | Expired users lose access; reminders sent |  |  |  | None | Not Tested | 0% | 0% | 13 |  | ⏳ 2 open | Phase 5¦10 | 46319.0008 |  | On track
P5-11 | Phase 5 | Member Dashboard | Member dashboard | Account page: profile edit, plan & expiry, payment history, downloads, saved issues, logout. | P0 | Not Started | 2026-10-24 | 2026-10-24 | 0% | P5-04, P5-07 | Staging (Hostinger) | page-templates/page-account.php | Check as free, member and subscriber | Members manage account and see entitlements |  |  |  | None | Not Tested | 0% | 0% | 13 |  | ⏳ 2 open | Phase 5¦11 | 46319.0008 |  | On track
P5-12 | Phase 5 | Security | Security hardening & rate limiting | Login/registration/reset rate limiting by IP + account, nonces on all forms, CAPTCHA/Turnstile or honeypot, password policy, generic error messages, sanitize/escape audit of auth code. | P0 | Not Started | 2026-10-24 | 2026-10-24 | 0% | P5-04 | Staging (Hostinger) | inc/security.php | Brute-force 10 attempts → lockout; CSRF test without nonce | Abuse throttled; no user enumeration; forms CSRF-safe |  |  |  | None | Not Tested | 0% | 0% | 13 |  | ⏳ 1 open | Phase 5¦12 | 46319.0009 |  | On track
P5-13 | Phase 5 | Email | SMTP / transactional email setup | Configure authenticated SMTP (SPF/DKIM) for verification, reset, receipts and lead notifications. | P0 | Not Started | 2026-10-24 | 2026-10-25 | 0% |  | Staging (Hostinger) | wp-config.php or SMTP plugin settings | Send test emails to Gmail/Outlook; check spam | Transactional emails delivered to inbox |  |  |  | Credentials | Not Tested | 0% | 0% | 14 |  |  | Phase 5¦13 | 46320.0009 |  | External req.
P5-14 | Phase 5 | AdOps | Advertising page | page-advertise.php: audience stats, placements, formats, CTA to lead form and media kit. | P1 | Not Started | 2026-10-25 | 2026-10-25 | 0% | P1-17 | Staging (Hostinger) | page-templates/page-advertise.php | Content review with client; responsive check | Advertising page live with editable content |  |  |  | Client Content | Not Tested | 0% | 0% | 14 |  | ⏳ 1 open | Phase 5¦14 | 46320.0009 |  | External req.
P5-15 | Phase 5 | AdOps | Advertising rate calculator | Vanilla JS calculator: placement, size, duration, frequency → estimated price; rates editable in admin (no code). | P1 | Not Started | 2026-10-25 | 2026-10-25 | 0% | P5-14 | Staging (Hostinger) | assets/js/modules/rate-calculator.js, inc/adops-settings.php | Test edge values; change a rate in admin | Calculator accurate and admin-configurable |  |  |  | Client Content | Not Tested | 0% | 0% | 14 |  | ⏳ 1 open | Phase 5¦15 | 46320.0009 |  | External req.
P5-16 | Phase 5 | AdOps | Media kit download | Media kit PDF download, optionally gated behind lead form. | P2 | Not Started | 2026-10-25 | 2026-10-25 | 0% | P5-14, P5-17 | Staging (Hostinger) | page-templates/page-advertise.php | Download after form submit | Media kit downloadable and tracked |  |  |  | Client Content | Not Tested | 0% | 0% | 14 |  | ⏳ 2 open | Phase 5¦16 | 46320.0009 |  | External req.
P5-17 | Phase 5 | Leads | Lead capture forms | Advertising inquiry & general lead forms stored as private 'lead' CPT + email notification; spam protection; admin export CSV. | P0 | Not Started | 2026-10-25 | 2026-10-25 | 0% | P5-12, P5-13 | Staging (Hostinger) | inc/leads.php | Submit valid/invalid/spam; export CSV | Every lead stored and notified; spam blocked |  |  |  | None | Not Tested | 0% | 0% | 14 |  | ⏳ 2 open | Phase 5¦17 | 46320.0009 |  | On track
P5-18 | Phase 5 | Pages | About page | page-about.php: mission, history, team, partners; editable via blocks/ACF-free fields. | P1 | Not Started | 2026-10-25 | 2026-10-25 | 0% | P1-17 | Staging (Hostinger) | page-templates/page-about.php | Content review; responsive check | About page live and editable |  |  |  | Client Content | Not Tested | 0% | 0% | 14 |  | ⏳ 1 open | Phase 5¦18 | 46320.0009 |  | External req.
P5-19 | Phase 5 | Pages | Contact page | page-contact.php: contact form (stored + emailed), details, map embed (lazy), social links. | P0 | Not Started | 2026-10-25 | 2026-10-25 | 0% | P5-17 | Staging (Hostinger) | page-templates/page-contact.php | Submit form; check stored entry and email | Contact form works end-to-end |  |  |  | None | Not Tested | 0% | 0% | 14 |  | ⏳ 1 open | Phase 5¦19 | 46320.0009 |  | On track
P5-20 | Phase 5 | Roles | Editorial roles & permissions | Define roles/capabilities: Editor-in-Chief, Editor, Writer/Contributor, Ad Manager, Subscriber tiers; restrict Customizer/Section Manager to editors+. | P0 | Not Started | 2026-10-25 | 2026-10-25 | 0% | P2-02 | Staging (Hostinger) | inc/roles.php | Log in as each role; attempt forbidden actions | Each role can do exactly what it needs and nothing more |  |  |  | None | Not Tested | 0% | 0% | 14 |  | ⏳ 1 open | Phase 5¦20 | 46320.0009 |  | On track
P6-01 | Phase 6 | Backup | Full production backup (files + DB) before any work | Full backup of production files (incl. large uploads) and database; store off-server; verify archive integrity and restore-test on staging. | P0 | Not Started | 2026-10-12 | 2026-10-12 | 0% |  | Production | backups/ (off-server) | Checksum verified; DB dump imports cleanly on staging | Restorable backup exists before any change |  |  |  | Server Access | Not Tested | 0% | 0% | 1 |  |  | Phase 6¦1 | 46307.001 |  | Due soon
P6-02 | Phase 6 | Backup | Verify staging mirrors production | Confirm staging DB/content is a current copy: post count (2,645 articles), media, users, menus, plugins; record content-freeze or delta-sync approach. | P0 | Not Started | 2026-10-12 | 2026-10-12 | 0% | P6-01 | Staging (Hostinger) | wp-config.php, database | Compare post/term/user counts staging vs production | Staging is a verified mirror; content-delta plan agreed |  |  |  | Server Access | Not Tested | 0% | 0% | 1 |  | ⏳ 1 open | Phase 6¦2 | 46307.001 |  | Due soon
P6-03 | Phase 6 | DB Audit | Database audit | Table sizes, autoloaded options size, revisions, expired transients, orphaned postmeta/termmeta, JNews options and tables; document findings. | P0 | Not Started | 2026-10-13 | 2026-10-13 | 0% | P6-02 | Staging (Hostinger) | database (phpMyAdmin) | Run audit queries; export results | Audit report saved; risks logged |  |  |  | None | Not Tested | 0% | 0% | 2 |  | ⏳ 1 open | Phase 6¦3 | 46308.001 |  | Due soon
P6-04 | Phase 6 | JNews Review | Legacy JNews dependency review | Inventory JNews shortcodes in post_content, JNews postmeta in use (views, subtitle, video, gallery), widgets, menus, and plugins depending on JNews; decide keep/convert/drop for each. | P0 | Not Started | 2026-10-13 | 2026-10-13 | 0% | P6-03 | Staging (Hostinger) | database, wp-content/plugins/jnews-* | SQL LIKE search for shortcodes; meta key frequency list | Every JNews dependency has a documented decision |  |  |  | None | Not Tested | 0% | 0% | 2 |  | ⏳ 1 open | Phase 6¦4 | 46308.001 |  | Due soon
P6-05 | Phase 6 | URL Inventory | Export URL inventory (2,645 articles + taxonomies) | Export all article, category, tag, author, page URLs from production sitemaps/DB into url-inventory.csv. | P0 | Not Started | 2026-10-13 | 2026-10-13 | 0% | P6-01 | Production | url-inventory.csv | Row count = 2,645 articles + taxonomy/page rows | Complete URL inventory saved |  |  |  | None | Not Tested | 0% | 0% | 2 |  | ⏳ 1 open | Phase 6¦5 | 46308.001 |  | Due soon
P6-06 | Phase 6 | SEO Baseline | Capture SEO baseline | Crawl production: titles, meta descriptions, canonicals, H1, robots, hreflang/OG, schema, sitemap; export Search Console coverage & top pages. | P0 | Not Started | 2026-10-13 | 2026-10-13 | 0% | P6-05 | Production | seo-baseline.csv | Baseline crawl complete; GSC export saved | Baseline available for comparison |  |  |  | Credentials | Not Tested | 0% | 0% | 2 |  | ⏳ 1 open | Phase 6¦6 | 46308.001 |  | Due soon
P6-07 | Phase 6 | DB Optimization | Safe database optimization (staging first) | Limit revisions, delete expired transients, orphan meta, trim autoload; only after backup; replicate on production only during cutover window. | P1 | Not Started | 2026-10-26 | 2026-10-26 | 0% | P6-03, P6-04 | Staging (Hostinger) | wp-config.php (WP_POST_REVISIONS), database | Before/after sizes; site regression check | DB smaller and faster with no content loss |  |  |  | None | Not Tested | 0% | 0% | 15 |  | ⏳ 2 open | Phase 6¦7 | 46321.001 |  | On track
P6-08 | Phase 6 | URL Validation | Validate all 2,645 article URLs on staging | Crawl/script all inventory URLs against staging (host-swapped): expect 200, same permalink, correct template; list any 404/redirect. | P0 | Not Started | 2026-10-26 | 2026-10-26 | 0% | P6-05, P3-16 | Staging (Hostinger) | url-inventory.csv | Automated crawl; 0 unexpected 404s | 2,645/2,645 article URLs return 200 with correct content |  |  |  | None | Not Tested | 0% | 0% | 15 |  | ⏳ 2 open | Phase 6¦8 | 46321.001 |  | On track
P6-09 | Phase 6 | SEO | SEO comparison: staging vs baseline | Diff titles, metas, canonicals, H1, schema, robots between staging and baseline; fix regressions. | P0 | Not Started | 2026-10-26 | 2026-10-27 | 0% | P6-06, P6-08 | Staging (Hostinger) | seo-baseline.csv | Diff report reviewed | No SEO regressions vs baseline |  |  |  | None | Not Tested | 0% | 0% | 16 |  | ⏳ 2 open | Phase 6¦9 | 46322.001 |  | On track
P6-10 | Phase 6 | SEO | 301 redirect map for changed URLs | Map any changed URLs (e.g. JNews-specific pages, issue URLs) to new destinations; implement and test. | P1 | Not Started | 2026-10-27 | 2026-10-27 | 0% | P6-08 | Staging (Hostinger) | inc/redirects.php or Redirection export | .htaccess / plugin test of each mapping | All changed URLs 301 to correct targets; no chains |  |  |  | None | Not Tested | 0% | 0% | 16 |  | ⏳ 1 open | Phase 6¦10 | 46322.001 |  | On track
P6-11 | Phase 6 | Performance | Performance optimization (Core Web Vitals) | Critical CSS, font preload, image sizes, query counts, defer non-critical JS; targets LCP < 2.5 s, CLS < 0.1, INP < 200 ms on mobile. | P0 | Not Started | 2026-10-27 | 2026-10-28 | 0% | P2-24, P3-16, P4-12 | Staging (Hostinger) | inc/enqueue.php, assets/* | Lighthouse/PageSpeed on homepage, article, category, issue | Key templates meet Core Web Vitals targets on mobile |  |  |  | None | Not Tested | 0% | 0% | 17 |  | ⏳ 3 open | Phase 6¦11 | 46323.001 |  | On track
P6-12 | Phase 6 | Caching | LiteSpeed Cache configuration | Page cache, object cache (if available), browser cache, CSS/JS minify compatible with theme, image optimization; exclude login/account/checkout/webhook URLs; purge rules for publish. | P0 | Not Started | 2026-10-28 | 2026-10-28 | 0% | P6-11, P2-08 | Staging (Hostinger) | LiteSpeed Cache settings | Logged-in vs guest caching; checkout not cached; purge on publish | Fast cached pages with no cached private content |  |  |  | Server Access | Not Tested | 0% | 0% | 17 |  | ⏳ 2 open | Phase 6¦12 | 46323.0011 |  | External req.
P6-13 | Phase 6 | Testing | Responsive testing | Run QA responsive matrix on all nine templates at 360–1440 px and real devices. | P0 | Not Started | 2026-10-28 | 2026-10-28 | 0% | P6-11 | Staging (Hostinger) | — | QA sheet: Mobile Responsiveness rows | All templates pass responsive checks |  |  |  | None | Not Tested | 0% | 0% | 17 |  | ⏳ 1 open | Phase 6¦13 | 46323.0011 |  | On track
P6-14 | Phase 6 | Testing | Cross-browser testing | Chrome, Safari (macOS/iOS), Firefox, Edge, Samsung Internet. | P0 | Not Started | 2026-10-28 | 2026-10-29 | 0% | P6-13 | Staging (Hostinger) | — | QA sheet: Browser Compatibility rows | No blocking issues in supported browsers |  |  |  | None | Not Tested | 0% | 0% | 18 |  | ⏳ 1 open | Phase 6¦14 | 46324.0011 |  | On track
P6-15 | Phase 6 | Security | Security verification | File permissions, disable file editing, XML-RPC policy, user enumeration, security headers, plugin updates, nonce/escaping audit, admin accounts review. | P0 | Not Started | 2026-10-29 | 2026-10-29 | 0% | P5-12 | Staging + Production | wp-config.php, .htaccess | QA sheet: Security rows; header scan | No high-severity findings open |  |  |  | Server Access | Not Tested | 0% | 0% | 18 |  | ⏳ 1 open | Phase 6¦15 | 46324.0011 |  | External req.
P6-16 | Phase 6 | Testing | Full QA regression run | Execute every row in the QA & Testing sheet; log defects. | P0 | Not Started | 2026-10-29 | 2026-10-30 | 0% | P6-13, P6-14 | Staging (Hostinger) | — | QA sheet completion = 100% | All P0 test cases pass |  |  |  | None | Not Tested | 0% | 0% | 19 |  | ⏳ 2 open | Phase 6¦16 | 46325.0011 |  | On track
P6-17 | Phase 6 | Bug Fixing | Defect fixing buffer | Reserved time to fix defects from QA and client UAT. | P0 | Not Started | 2026-10-30 | 2026-10-31 | 0% | P6-16 | Staging (Hostinger) | — | Re-test fixed defects | No open P0/P1 defects |  |  |  | None | Not Tested | 0% | 0% | 20 |  | ⏳ 1 open | Phase 6¦17 | 46326.0011 |  | On track
P6-18 | Phase 6 | Readiness | Deployment readiness review & client UAT sign-off | Walk client through staging; obtain written approval; confirm live payment approval, credentials for production domain, content freeze window. | P0 | Not Started | 2026-10-31 | 2026-10-31 | 0% | P6-17 | Staging (Hostinger) | — | Deployment sheet stage 1 complete | Written client approval to deploy |  |  |  | None | Not Tested | 0% | 0% | 20 |  | ⏳ 1 open | Phase 6¦18 | 46326.0011 |  | On track
P6-19 | Phase 6 | Rollback | Rollback plan documented & rehearsed | Rehearse restore of backup + theme switch-back on staging; time it; record in Deployment sheet. | P0 | Not Started | 2026-10-31 | 2026-10-31 | 0% | P6-01 | Staging (Hostinger) | Deployment & Rollback sheet | Timed rehearsal | Rollback achievable within agreed window (target < 30 min) |  |  |  | Server Access | Not Tested | 0% | 0% | 20 |  | ⏳ 1 open | Phase 6¦19 | 46326.0011 |  | External req.
P6-20 | Phase 6 | Backup | Fresh pre-cutover production backup | New full files + DB backup immediately before cutover; verify. | P0 | Not Started | 2026-10-31 | 2026-10-31 | 0% | P6-18 | Production | backups/ (off-server) | Checksum + test import | Verified backup timestamped before cutover |  |  |  | Server Access | Not Tested | 0% | 0% | 20 |  | ⏳ 1 open | Phase 6¦20 | 46326.0011 |  | External req.
P6-21 | Phase 6 | Cutover | Production cutover | Deploy theme & required plugins, migrate issues/settings/Customizer/roles, run approved DB optimizations, activate theme, switch credentials & webhooks to production, purge caches. | P0 | Not Started | 2026-11-01 | 2026-11-01 | 0% | P6-18, P6-19, P6-20 | Production | theme package, settings exports | Follow Deployment sheet stages 5–7 | New site live on production with no data loss |  |  |  | Server Access | Not Tested | 0% | 0% | 21 |  | ⏳ 3 open | Phase 6¦21 | 46327.0011 |  | External req.
P6-22 | Phase 6 | Post-launch | Post-launch verification & monitoring | Smoke tests, URL sample crawl, Search Console sitemap resubmit, payments live test, error log and uptime monitoring for 48 h. | P0 | Not Started | 2026-11-01 | 2026-11-01 | 0% | P6-21 | Production | debug.log, Search Console | Deployment sheet stage 8–9 | No critical issues in first 48 h |  |  |  | None | Not Tested | 0% | 0% | 21 |  | ⏳ 1 open | Phase 6¦22 | 46327.0012 |  | On track
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%
[20 empty] | 0% | 0%

## P1 Theme Foundation
PHASE 1 — THEME FOUNDATION & ASSET PIPELINE
Window 12 Oct – 14 Oct 2026 · Status is read live from the Master Tracker (edit there)
← Dashboard |  |  | Open Master Tracker → |  | Staging ↗
COMPLETION |  |  | PLANNED | TASKS |  | DONE | IN PROGRESS |  | BLOCKED |  | OVERDUE | IN REVIEW / TEST | OPEN P0 | DEADLINE | PHASE STATUS
11.76% |  |  | 0% | 17 |  | 2 | 0 |  | 0 |  | 0 | 0 | 12 | 2026-10-14 | On Track
Progress ██████░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░ 12% (planned 0%)
PHASE GOAL
Build a clean, dependency-free custom WordPress theme (replacing JNews) with a modular PHP template system, a token-based CSS architecture, Vanilla JS modules, first-class Arabic RTL typography, responsive layouts, and performance primitives (query caching, Arabic date helpers) that every later phase reuses.
DELIVERABLES | [8 empty] | REQUIRED WORDPRESS FILES
▸ Custom theme 'altijara' activated on staging | [8 empty] | ▸ style.css
▸ Theme initialization (supports, menus, image sizes, text domain) | [8 empty] | ▸ functions.php
▸ Base PHP template hierarchy + reusable components | [8 empty] | ▸ inc/setup.php
▸ CSS token architecture & Vanilla JS module system | [8 empty] | ▸ inc/enqueue.php
▸ RTL Arabic typography and responsive grid | [8 empty] | ▸ inc/cache.php
▸ Header / navigation / footer | [8 empty] | ▸ inc/helpers-date.php
▸ Query caching layer + Arabic date helpers | [8 empty] | ▸ inc/media.php
▸ Git repository of theme (backup of staging work) | [8 empty] | ▸ inc/widgets.php
▸ header.php / footer.php
▸ index.php, front-page.php, single.php, page.php
▸ archive.php, category.php, tag.php, author.php, search.php, 404.php
▸ template-parts/components/*.php
▸ assets/css/*.css, assets/js/*.js, assets/fonts/*
TECHNICAL IMPLEMENTATION STEPS
1 | Audit staging access (hPanel, SFTP/SSH, phpMyAdmin), block indexing, enable debug log
2 | Scaffold /wp-content/themes/altijara/ and commit to Git
3 | Write inc/setup.php (theme supports, menus, image sizes)
4 | Write inc/enqueue.php with filemtime versioning and conditional loading
5 | Create template hierarchy skeletons and template-parts/components
6 | Build tokens.css → base → layout → components → utilities using logical properties
7 | Build main.js module loader (nav, drawer, search) without jQuery
8 | Self-host Arabic WOFF2 fonts, set dir=rtl / lang=ar
9 | Implement inc/cache.php with publish-time invalidation
10 | Implement inc/helpers-date.php; verify with Query Monitor and debug.log
DETAILED TASK CHECKLIST (live from Master Tracker — change Status / % there)
# | Task ID | Module | Task | Priority | Status | Start | Due | Complete | Dependencies | Dep. check | WordPress files | Acceptance criteria | Testing checklist | Test result | Alert
1 | P1-01 | Staging Setup | Staging environment readiness audit | P0 | Completed | 2026-10-12 | 2026-10-12 | 100% | P6-02 | ⏳ 1 open | wp-config.php, .htaccess | Staging is reachable only by the team, not indexed, debug logging active, versions documented in Notes | Log in via hPanel, SFTP and phpMyAdmin; confirm noindex header; send test mail is trapped | Not Tested | Done | 1
2 | P1-02 | Theme Scaffold | Create custom theme structure + Git repo | P0 | Completed | 2026-10-12 | 2026-10-12 | 100% | P1-01 | ✓ Ready | style.css, functions.php, inc/, template-parts/, assets/ | Folder structure in place, theme activates cleanly on staging, repository holds initial commit | Theme listed in Appearance > Themes; activates with no PHP notices; first commit pushed | Not Tested | Done | 2
3 | P1-03 | Theme Initialization | Theme setup: supports, menus, image sizes | P0 | Not Started | 2026-10-12 | 2026-10-12 | 0% | P1-02 | ✓ Ready | inc/setup.php, functions.php | All supports, menus and image sizes registered; no duplicate title tags | Menus appear in Appearance > Menus; new upload generates all image sizes; single <title> tag | Not Tested | Due soon | 3
4 | P1-04 | Asset Pipeline | Asset enqueue, versioning & conditional loading | P0 | Not Started | 2026-10-12 | 2026-10-12 | 0% | P1-02 | ✓ Ready | inc/enqueue.php, assets/css/*, assets/js/* | All assets versioned and loaded only where needed; zero console errors | View source: versioned URLs, deferred scripts; Network tab shows no 404s and no jQuery on homepage | Not Tested | Due soon | 4
5 | P1-05 | PHP Templates | Base template hierarchy | P0 | Not Started | 2026-10-12 | 2026-10-12 | 0% | P1-03 | ⏳ 1 open | header.php, footer.php, index.php, front-page.php, single.php, page.php, archive.php, category.php, tag.php, author.php, search.php, 404.php | Every WordPress route resolves to a theme template with header/footer; no fallback errors | Visit each route type; Query Monitor confirms expected template file | Not Tested | Due soon | 5
6 | P1-06 | Components | Reusable template-part components | P0 | Not Started | 2026-10-12 | 2026-10-12 | 0% | P1-05 | ⏳ 1 open | template-parts/components/*.php | Components reused by homepage and archives with no duplicated markup; all output escaped | Render every component on a test page with real posts; test missing image/excerpt; check escaping | Not Tested | Due soon | 6
7 | P1-07 | CSS Architecture | CSS architecture & design tokens | P0 | Not Started | 2026-10-12 | 2026-10-13 | 0% | P1-04 | ⏳ 1 open | assets/css/tokens.css, base.css, layout.css, components.css, utilities.css | Single token source; consistent styling; total CSS within agreed budget (target < 100 KB uncompressed) | Inspect computed styles use tokens; RTL correct without separate override file; CSS size checked | Not Tested | Due soon | 7
8 | P1-08 | Vanilla JS | Vanilla JS module architecture | P0 | Not Started | 2026-10-13 | 2026-10-13 | 0% | P1-04 | ⏳ 1 open | assets/js/main.js, assets/js/modules/*.js | All interactions implemented in Vanilla JS; zero console errors; scripts deferred | Console clean on Chrome & Safari; page usable with JS disabled | Not Tested | Due soon | 8
9 | P1-09 | RTL Typography | RTL layout & Arabic typography | P0 | Not Started | 2026-10-13 | 2026-10-13 | 0% | P1-07 | ⏳ 1 open | assets/fonts/*, assets/css/base.css, header.php | Correct RTL direction site-wide; fonts self-hosted; no layout shift from font swap | Headlines/body render in Arabic font on iOS, Android, desktop; no invisible text flash; mixed strings align | Not Tested | Due soon | 9
10 | P1-10 | Responsive Design | Responsive grid & breakpoints | P0 | Not Started | 2026-10-13 | 2026-10-13 | 0% | P1-07 | ⏳ 1 open | assets/css/layout.css | All layouts usable at 360 px; no overflow; correctly sized images | Test 360, 414, 768, 1024, 1440 px widths; no horizontal scroll | Not Tested | Due soon | 10
11 | P1-11 | Header & Navigation | Header, navigation, mobile drawer & search | P0 | Not Started | 2026-10-13 | 2026-10-14 | 0% | P1-06, P1-08, P1-15 | ⏳ 3 open | header.php, template-parts/header/*.php, assets/js/modules/nav.js | Navigation works on touch and keyboard; fully managed from WordPress menus | Drawer opens/closes, Esc closes, focus trapped; search submits; menu edited in WP admin updates header | Not Tested | On track | 11
12 | P1-12 | Footer | Footer with editable menus & social links | P1 | Not Started | 2026-10-14 | 2026-10-14 | 0% | P1-06 | ⏳ 1 open | footer.php, template-parts/footer/*.php | Footer content editable without code | All links resolve; social URLs editable in Customizer | Not Tested | On track | 12
13 | P1-13 | WordPress Integration | Core WordPress integration & editor styles | P0 | Not Started | 2026-10-14 | 2026-10-14 | 0% | P1-05 | ⏳ 1 open | functions.php, inc/widgets.php, assets/css/editor-style.css | Theme compatible with WordPress core and active plugins; no missing hooks | SEO and LiteSpeed plugins inject head tags; widgets render; editor preview matches front end | Not Tested | On track | 13
14 | P1-14 | Query Caching | Query caching layer with auto-invalidation | P0 | Not Started | 2026-10-14 | 2026-10-14 | 0% | P1-03 | ⏳ 1 open | inc/cache.php | Homepage warm-cache DB queries within target (≤ 40); no stale content after publish | Query Monitor shows reduced queries on warm load; publishing a post refreshes affected sections immediately | Not Tested | On track | 14
15 | P1-15 | Date Helpers | Arabic date, relative time & reading-time helpers | P1 | Not Started | 2026-10-14 | 2026-10-14 | 0% | P1-03 | ⏳ 1 open | inc/helpers-date.php | All templates use helpers; dates correct in site timezone | Check outputs for today, yesterday, last month and last year in site timezone | Not Tested | On track | 15
16 | P1-16 | Media | Image handling, lazy-load & fallbacks | P1 | Not Started | 2026-10-14 | 2026-10-14 | 0% | P1-06 | ⏳ 1 open | inc/media.php, template-parts/components/* | Every card shows an image or fallback; CLS < 0.1 on archives | Legacy post without featured image shows fallback; no layout shift on card grids | Not Tested | On track | 16
17 | P1-17 | Phase QA | Phase 1 verification & tag v0.1 | P0 | Not Started | 2026-10-14 | 2026-10-14 | 0% | P1-11, P1-13, P1-14, P1-16 | ⏳ 4 open | debug.log | Foundation signed off; Phase 2 can start | debug.log has no theme notices; all templates load | Not Tested | On track | 17
18
19
20
21
22
23
24
25

## P2 Homepage & Sections
PHASE 2 — HOMEPAGE & DYNAMIC SECTION MANAGER
Window 15 Oct – 17 Oct 2026 · Status is read live from the Master Tracker (edit there)
← Dashboard |  |  | Open Master Tracker → |  | Staging ↗
COMPLETION |  |  | PLANNED | TASKS |  | DONE | IN PROGRESS |  | BLOCKED |  | OVERDUE | IN REVIEW / TEST | OPEN P0 | DEADLINE | PHASE STATUS
0% |  |  | 0% | 24 |  | 0 | 0 |  | 0 |  | 0 | 0 | 11 | 2026-10-17 | Not Started
Progress ░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░ 0% (planned 0%)
PHASE GOAL
Deliver a fully dynamic magazine homepage whose every section (source, count, order, offset, layout, visibility, cache) is controlled by editors through the WordPress Customizer Section Manager — no code changes needed to re-arrange the homepage.
DELIVERABLES | [8 empty] | REQUIRED WORDPRESS FILES
▸ Section Manager engine with per-section schema | [8 empty] | ▸ front-page.php
▸ Customizer 'Homepage Sections' panel with sanitized controls | [8 empty] | ▸ inc/section-manager/registry.php
▸ Category/tag selectors, manual post picker, count/sort/offset controls | [8 empty] | ▸ inc/section-manager/query-builder.php
▸ Layout switching, visibility toggles, ordering, de-duplication | [8 empty] | ▸ inc/section-manager/render.php
▸ Section cache controls + LiteSpeed purge | [8 empty] | ▸ inc/customizer/panel-homepage.php
▸ Hero, breaking ticker, cover slider, chamber, opinion, reports, article grids | [8 empty] | ▸ inc/customizer/controls/*.php
▸ Business, Real Estate, Automotive, Technology, Healthcare, Tourism sections | [8 empty] | ▸ assets/js/customizer-controls.js
▸ Most-read widget and homepage ad slots | [8 empty] | ▸ assets/js/modules/ticker.js, slider.js
▸ template-parts/sections/*.php
▸ inc/most-read.php
▸ inc/widgets/most-read-widget.php
TECHNICAL IMPLEMENTATION STEPS
1 | Define section schema & registry in inc/section-manager/
2 | Build WP_Query args builder (source, count, orderby, offset, exclusions)
3 | Register Customizer panel/sections/settings with sanitize callbacks
4 | Create custom controls: term multi-select, post picker (REST), sortable order
5 | Map layouts to template-parts components
6 | Wrap every section query in altijara_cached_query with TTL
7 | Add purge button + auto-purge on publish + LiteSpeed purge action
8 | Build hero, ticker (Vanilla JS), cover slider (CPT-driven)
9 | Configure each sector section via Section Manager
10 | Implement view counter + most-read widget; measure queries with Query Monitor
DETAILED TASK CHECKLIST (live from Master Tracker — change Status / % there)
# | Task ID | Module | Task | Priority | Status | Start | Due | Complete | Dependencies | Dep. check | WordPress files | Acceptance criteria | Testing checklist | Test result | Alert
1 | P2-01 | Section Manager | Section Manager engine & schema | P0 | Not Started | 2026-10-15 | 2026-10-15 | 0% | P1-06, P1-14 | ⏳ 2 open | inc/section-manager/registry.php, query-builder.php, render.php | Every homepage section is rendered from the registry; no hard-coded queries in front-page.php | Register a test section; change schema values; output changes accordingly | Not Tested | On track | 18
2 | P2-02 | Customizer | Customizer 'Homepage Sections' panel | P0 | Not Started | 2026-10-15 | 2026-10-15 | 0% | P2-01 | ⏳ 1 open | inc/customizer/panel-homepage.php, assets/js/customizer-preview.js | All sections configurable in Customizer with live preview and sanitized values | Editor (non-admin) changes a section in Customizer and publishes; invalid values rejected | Not Tested | On track | 19
3 | P2-03 | Customizer Controls | Dynamic category / tag selection | P0 | Not Started | 2026-10-15 | 2026-10-15 | 0% | P2-02 | ⏳ 1 open | inc/customizer/controls/term-select.php, assets/js/customizer-controls.js | Sections can be sourced from any category/tag combination by ID | Select 2 categories + 1 tag; rename a category; section still pulls correctly | Not Tested | On track | 20
4 | P2-04 | Customizer Controls | Post count, sorting & offset controls | P0 | Not Started | 2026-10-15 | 2026-10-15 | 0% | P2-03 | ⏳ 1 open | inc/section-manager/query-builder.php | Count, sorting and offset behave exactly as configured | Change count, order and offset; verify returned posts in Query Monitor | Not Tested | On track | 21
5 | P2-05 | Customizer Controls | Manual post selection (post picker) | P1 | Not Started | 2026-10-15 | 2026-10-15 | 0% | P2-02 | ⏳ 1 open | inc/customizer/controls/post-picker.php, assets/js/customizer-controls.js | Editors can pin specific posts in a chosen order | Pick 4 posts, reorder, publish; homepage shows them in chosen order | Not Tested | On track | 22
6 | P2-06 | Customizer Controls | Layout switching per section | P1 | Not Started | 2026-10-15 | 2026-10-15 | 0% | P2-01 | ⏳ 1 open | template-parts/sections/*.php | Each layout renders correctly and responsively | Switch each section through every layout at 360 px and 1440 px | Not Tested | On track | 23
7 | P2-07 | Customizer Controls | Section visibility, ordering & de-duplication | P0 | Not Started | 2026-10-15 | 2026-10-16 | 0% | P2-02 | ⏳ 1 open | inc/section-manager/render.php, inc/customizer/controls/sortable.php | Visibility, order and de-duplication controlled from Customizer | Hide a section, reorder two sections, confirm no duplicate posts across sections | Not Tested | On track | 24
8 | P2-08 | Cache Controls | Section cache controls + LiteSpeed purge | P0 | Not Started | 2026-10-16 | 2026-10-16 | 0% | P1-14, P2-01 | ⏳ 2 open | inc/section-manager/cache.php | Homepage never serves stale sections after publish; manual purge available | Publish a post → appears on homepage after purge; purge button works only for editors+ | Not Tested | On track | 25
9 | P2-09 | Homepage Sections | Homepage hero | P0 | Not Started | 2026-10-16 | 2026-10-16 | 0% | P2-01 | ⏳ 1 open | template-parts/sections/hero.php | Hero is editor-controlled and renders well on all breakpoints | Change hero source; check mobile crop and title wrapping in Arabic | Not Tested | On track | 26
10 | P2-10 | Homepage Sections | Breaking news ticker | P0 | Not Started | 2026-10-16 | 2026-10-16 | 0% | P2-01 | ⏳ 1 open | template-parts/sections/ticker.php, assets/js/modules/ticker.js | Ticker updates from WordPress, scrolls RTL and is accessible | Add/remove breaking tag; test RTL scroll direction, hover pause, reduced motion | Not Tested | On track | 27
11 | P2-11 | Homepage Sections | Magazine cover slider | P1 | Not Started | 2026-10-16 | 2026-10-16 | 0% | P2-01, P4-01 | ⏳ 2 open | template-parts/sections/cover-slider.php, assets/js/modules/slider.js | Slider shows latest issues automatically | Swipe on mobile; covers lazy-load; links open correct issue | Not Tested | On track | 28
12 | P2-12 | Homepage Sections | Chamber section | P1 | Not Started | 2026-10-16 | 2026-10-16 | 0% | P2-01 | ⏳ 1 open | template-parts/sections/* | Chamber section renders configured posts | Configure source and layout; verify output | Not Tested | On track | 29
13 | P2-13 | Homepage Sections | Opinion / columnists section | P1 | Not Started | 2026-10-16 | 2026-10-16 | 0% | P2-01 | ⏳ 1 open | template-parts/sections/opinion.php | Opinion section shows writers with working profile links | Check avatars, author links, fallback avatar | Not Tested | On track | 30
14 | P2-14 | Homepage Sections | Reports section | P1 | Not Started | 2026-10-16 | 2026-10-17 | 0% | P2-01 | ⏳ 1 open | template-parts/sections/* | Reports section renders configured posts | Configure; verify output and layout | Not Tested | On track | 31
15 | P2-15 | Homepage Sections | Latest news & article grid sections | P0 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-01 | ⏳ 1 open | template-parts/sections/grid.php | Article grids render and link to archives | Verify counts, links and de-duplication | Not Tested | On track | 32
16 | P2-16 | Sector Sections | Business section | P1 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-15 | ⏳ 1 open | template-parts/sections/* | Section live and editor-configurable | Verify source, count, layout | Not Tested | On track | 33
17 | P2-17 | Sector Sections | Real Estate section | P1 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-15 | ⏳ 1 open | template-parts/sections/* | Section live and editor-configurable | Verify source, count, layout | Not Tested | On track | 34
18 | P2-18 | Sector Sections | Automotive section | P1 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-15 | ⏳ 1 open | template-parts/sections/* | Section live and editor-configurable | Verify source, count, layout | Not Tested | On track | 35
19 | P2-19 | Sector Sections | Technology section | P1 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-15 | ⏳ 1 open | template-parts/sections/* | Section live and editor-configurable | Verify source, count, layout | Not Tested | On track | 36
20 | P2-20 | Sector Sections | Healthcare section | P1 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-15 | ⏳ 1 open | template-parts/sections/* | Section live and editor-configurable | Verify source, count, layout | Not Tested | On track | 37
21 | P2-21 | Sector Sections | Tourism section | P1 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-15 | ⏳ 1 open | template-parts/sections/* | Section live and editor-configurable | Verify source, count, layout | Not Tested | On track | 38
22 | P2-22 | Most Read | Most-read widget & view counter | P0 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P1-14, P6-04 | ⏳ 2 open | inc/most-read.php, inc/widgets/most-read-widget.php, assets/js/modules/views.js | Most-read list accurate, cached, and works with LiteSpeed page cache | Open articles in private windows; counts increase once per session; tabs switch | Not Tested | On track | 39
23 | P2-23 | AdOps | Homepage advertisement slots | P1 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-01 | ⏳ 1 open | template-parts/components/ad-slot.php | Ads managed without code; no CLS | Add an ad in Customizer; check placement & no layout shift | Not Tested | On track | 40
24 | P2-24 | Phase QA | Homepage performance & responsive sign-off | P0 | Not Started | 2026-10-17 | 2026-10-17 | 0% | P2-09, P2-10, P2-22 | ⏳ 3 open | front-page.php | Homepage meets performance targets and is approved for Phase 3 | Lighthouse mobile run; Query Monitor warm/cold; 360/768/1440 check | Not Tested | On track | 41
25
26
27
28
29
30
31
32

## P3 Editorial Templates
PHASE 3 — EDITORIAL & TAXONOMY TEMPLATES
Window 18 Oct – 20 Oct 2026 · Status is read live from the Master Tracker (edit there)
← Dashboard |  |  | Open Master Tracker → |  | Staging ↗
COMPLETION |  |  | PLANNED | TASKS |  | DONE | IN PROGRESS |  | BLOCKED |  | OVERDUE | IN REVIEW / TEST | OPEN P0 | DEADLINE | PHASE STATUS
0% |  |  | 0% | 16 |  | 0 | 0 |  | 0 |  | 0 | 0 | 8 | 2026-10-20 | Not Started
Progress ░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░ 0% (planned 0%)
PHASE GOAL
Provide production-grade article, author and taxonomy templates that render all 2,645 legacy articles correctly, support monetization (ad injection), engagement (sharing, related, progress bar) and discovery (AJAX filtering, grid/list, pagination) while remaining fully SEO-compatible.
DELIVERABLES | [8 empty] | REQUIRED WORDPRESS FILES
▸ Single article template with full metadata | [8 empty] | ▸ single.php
▸ Legacy JNews content/shortcode rendering | [8 empty] | ▸ author.php
▸ Reading progress bar, social sharing, related articles | [8 empty] | ▸ category.php
▸ In-article advertisement injection | [8 empty] | ▸ tag.php
▸ Author box and author profile template | [8 empty] | ▸ search.php
▸ Category, tag and search archives | [8 empty] | ▸ template-parts/article/*.php
▸ AJAX filtering, grid/list switching, pagination | [8 empty] | ▸ inc/content-filters.php
▸ Print stylesheet | [8 empty] | ▸ inc/legacy-shortcodes.php
▸ SEO plugin compatibility, schema & breadcrumbs | [8 empty] | ▸ inc/rest/archive-filter.php
▸ assets/js/modules/progress.js, share.js, filter.js
▸ assets/css/print.css
▸ inc/seo.php
TECHNICAL IMPLEMENTATION STEPS
1 | Build single.php from components; style content blocks & legacy markup
2 | Add shortcode fallbacks for JNews shortcodes found in audit (P6-04)
3 | Implement progress bar, share buttons (no third-party JS)
4 | Add the_content filter for ad injection by paragraph
5 | Build related query (category + tags, cached)
6 | Build author.php and category.php with featured lead
7 | Create REST endpoint for AJAX filtering with nonce + pushState
8 | Add grid/list toggle and SEO-friendly pagination
9 | Write print.css
10 | Verify SEO plugin output, NewsArticle schema, canonical, OG tags
DETAILED TASK CHECKLIST (live from Master Tracker — change Status / % there)
# | Task ID | Module | Task | Priority | Status | Start | Due | Complete | Dependencies | Dep. check | WordPress files | Acceptance criteria | Testing checklist | Test result | Alert
1 | P3-01 | Single Article | Single article template | P0 | Not Started | 2026-10-18 | 2026-10-18 | 0% | P1-17 | ⏳ 1 open | single.php, template-parts/article/*.php | Articles render correctly with full layout on all breakpoints | Open 20 sample articles across years and categories | Not Tested | On track | 42
2 | P3-02 | Article Metadata | Article metadata | P0 | Not Started | 2026-10-18 | 2026-10-18 | 0% | P3-01, P1-15 | ⏳ 2 open | template-parts/article/meta.php | Metadata accurate and localized | Compare metadata with WP admin values for 10 posts | Not Tested | On track | 43
3 | P3-03 | Legacy Content | Legacy JNews content & shortcode rendering | P0 | Not Started | 2026-10-18 | 2026-10-18 | 0% | P3-01, P6-04 | ⏳ 2 open | inc/legacy-shortcodes.php, assets/css/content.css | No raw shortcodes or broken legacy markup in any of the 2,645 articles | Open posts flagged in P6-04 audit; no raw [shortcodes] visible | Not Tested | On track | 44
4 | P3-04 | Engagement | Reading progress bar | P1 | Not Started | 2026-10-18 | 2026-10-18 | 0% | P3-01 | ⏳ 1 open | assets/js/modules/progress.js | Progress bar accurate, smooth, RTL | Scroll long article; check direction and smoothness on mobile | Not Tested | On track | 45
5 | P3-05 | Engagement | Social sharing | P1 | Not Started | 2026-10-18 | 2026-10-18 | 0% | P3-01 | ⏳ 1 open | template-parts/article/share.php, assets/js/modules/share.js | All share targets open with correct title and URL | Share each network; check URL encoding of Arabic titles | Not Tested | On track | 46
6 | P3-06 | AdOps | In-article advertisement injection | P1 | Not Started | 2026-10-18 | 2026-10-19 | 0% | P3-01, P2-23 | ⏳ 2 open | inc/content-filters.php | Ads appear at configured positions without breaking content | Test short, long and embed-heavy articles | Not Tested | On track | 47
7 | P3-07 | Engagement | Related articles | P1 | Not Started | 2026-10-19 | 2026-10-19 | 0% | P3-01, P1-14 | ⏳ 2 open | template-parts/article/related.php | Related list relevant and cached | Check relevance on 5 posts; check cache | Not Tested | On track | 48
8 | P3-08 | Author Profiles | Author box & author profile template | P0 | Not Started | 2026-10-19 | 2026-10-19 | 0% | P1-06 | ⏳ 1 open | author.php, template-parts/article/author-box.php | Every author has a working profile page | Open 5 author pages incl. one with no bio/avatar | Not Tested | On track | 49
9 | P3-09 | Category Archives | Category archive template | P0 | Not Started | 2026-10-19 | 2026-10-19 | 0% | P1-06 | ⏳ 1 open | category.php, archive.php | All categories render with correct posts and SEO-friendly URLs | Check every top-level category and 3 subcategories | Not Tested | On track | 50
10 | P3-10 | Taxonomy | Tag archive, search results & 404 | P1 | Not Started | 2026-10-19 | 2026-10-19 | 0% | P3-09 | ⏳ 1 open | tag.php, search.php, 404.php | Search returns relevant results; 404 helpful | Search Arabic terms; visit unknown URL | Not Tested | On track | 51
11 | P3-11 | AJAX Filtering | AJAX archive filtering | P1 | Not Started | 2026-10-19 | 2026-10-20 | 0% | P3-09 | ⏳ 1 open | inc/rest/archive-filter.php, assets/js/modules/filter.js | Filtering fast (< 500 ms server), shareable URLs, works without JS | Apply filters; use back button; disable JS and confirm links still work | Not Tested | On track | 52
12 | P3-12 | Archive UX | Grid / list view switching | P2 | Not Started | 2026-10-20 | 2026-10-20 | 0% | P3-09 | ⏳ 1 open | assets/js/modules/view-toggle.js | Toggle works on all archives | Toggle on archive; reload page; preference kept | Not Tested | On track | 53
13 | P3-13 | Pagination | Pagination | P0 | Not Started | 2026-10-20 | 2026-10-20 | 0% | P3-09 | ⏳ 1 open | template-parts/components/pagination.php | Pagination works on all archives without duplicate content issues | Navigate to last page of large category; check rel/canonical | Not Tested | On track | 54
14 | P3-14 | Print | Print stylesheet | P2 | Not Started | 2026-10-20 | 2026-10-20 | 0% | P3-01 | ⏳ 1 open | assets/css/print.css | Clean printable article | Print preview article in Chrome and Safari | Not Tested | On track | 55
15 | P3-15 | SEO | SEO compatibility, schema & breadcrumbs | P0 | Not Started | 2026-10-20 | 2026-10-20 | 0% | P3-01, P3-09, P6-06 | ⏳ 3 open | inc/seo.php, header.php | SEO output matches or improves baseline; valid structured data | Compare head tags with baseline; Rich Results test on 3 articles | Not Tested | On track | 56
16 | P3-16 | Phase QA | Editorial templates sign-off | P0 | Not Started | 2026-10-20 | 2026-10-20 | 0% | P3-03, P3-11, P3-15 | ⏳ 3 open | — | Templates approved for Phase 4 | QA sheet rows for templates 2–4 | Not Tested | On track | 57
17
18
19
20
21
22
23
24

## P4 Issues Archive
PHASE 4 — DIGITAL ISSUES ARCHIVE & CPT ENGINE
Window 21 Oct – 22 Oct 2026 · Status is read live from the Master Tracker (edit there)
← Dashboard |  |  | Open Master Tracker → |  | Staging ↗
COMPLETION |  |  | PLANNED | TASKS |  | DONE | IN PROGRESS |  | BLOCKED |  | OVERDUE | IN REVIEW / TEST | OPEN P0 | DEADLINE | PHASE STATUS
0% |  |  | 0% | 12 |  | 0 | 0 |  | 0 |  | 0 | 0 | 9 | 2026-10-22 | Not Started
Progress ░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░ 0% (planned 0%)
PHASE GOAL
Create a magazine-issue engine (custom post type) and migrate all 48 historical issues with covers and PDFs into a filterable digital archive featuring a flipbook reader, secure PDF downloads and subscription-aware access restrictions.
DELIVERABLES | [8 empty] | REQUIRED WORDPRESS FILES
▸ magazine_issue CPT + fields (number, date, year, decade, PDF, access level) | [8 empty] | ▸ inc/cpt-issues.php
▸ All 48 historical issues migrated with covers and PDFs | [8 empty] | ▸ inc/issue-meta.php
▸ Issue archive with year and decade filtering | [8 empty] | ▸ inc/issue-import.php
▸ Single issue page | [8 empty] | ▸ archive-magazine_issue.php
▸ Flipbook reader with mobile fallback | [8 empty] | ▸ single-magazine_issue.php
▸ Secure PDF downloads | [8 empty] | ▸ template-parts/issue/*.php
▸ Access restrictions tied to subscription tiers | [8 empty] | ▸ inc/pdf-download.php
▸ assets/js/modules/flipbook.js
▸ assets/vendor/pdfjs/*
▸ .htaccess (protected uploads rule)
TECHNICAL IMPLEMENTATION STEPS
1 | Register CPT & meta in inc/cpt-issues.php (REST enabled)
2 | Collect 48 PDFs + covers + manifest from client (started Day 1)
3 | Build CSV manifest and idempotent importer (WP-CLI or one-time admin tool)
4 | Optimize covers (WebP, sizes)
5 | Build archive-magazine_issue.php with year/decade filters
6 | Build single-magazine_issue.php
7 | Integrate self-hosted PDF.js flipbook, lazy-loaded
8 | Serve PDFs via authenticated endpoint; block direct /uploads access
9 | Wire access level to subscription tiers (P5-07)
10 | Verify 48/48 issues
DETAILED TASK CHECKLIST (live from Master Tracker — change Status / % there)
# | Task ID | Module | Task | Priority | Status | Start | Due | Complete | Dependencies | Dep. check | WordPress files | Acceptance criteria | Testing checklist | Test result | Alert
1 | P4-01 | CPT Engine | Register magazine_issue custom post type | P0 | Not Started | 2026-10-21 | 2026-10-21 | 0% | P1-17 | ⏳ 1 open | inc/cpt-issues.php | CPT live with clean URLs | Create test issue; check archive URL and REST response; flush permalinks | Not Tested | On track | 58
2 | P4-02 | CPT Engine | Issue fields: number, date, year, decade, PDF, access | P0 | Not Started | 2026-10-21 | 2026-10-21 | 0% | P4-01 | ⏳ 1 open | inc/issue-meta.php | All issue metadata editable and validated | Save issue; decade auto-calculates; invalid values rejected | Not Tested | On track | 59
3 | P4-03 | Historical Assets | Collect 48 historical issue PDFs, covers & manifest | P0 | Not Started | 2026-10-12 | 2026-10-20 | 0% |  |  | url: shared drive | All historical assets received and checked | Count received files = 48 PDFs + 48 covers; manifest complete | Not Tested | External req. | 60
4 | P4-04 | Migration | Historical issue migration (import 48 issues) | P0 | Not Started | 2026-10-21 | 2026-10-21 | 0% | P4-02, P4-03 | ⏳ 2 open | inc/issue-import.php, issues-manifest.csv | All 48 issues imported with correct metadata, covers and PDFs | Run import twice; still 48 issues; spot-check 10 | Not Tested | External req. | 61
5 | P4-05 | Cover Images | Cover image optimization | P1 | Not Started | 2026-10-21 | 2026-10-21 | 0% | P4-04 | ⏳ 1 open | inc/media.php | Covers sharp and lightweight | Check archive weight and image dimensions | Not Tested | On track | 62
6 | P4-06 | Issue Archive | Issue archive template | P0 | Not Started | 2026-10-21 | 2026-10-21 | 0% | P4-01 | ⏳ 1 open | archive-magazine_issue.php, template-parts/issue/card.php | Archive lists all issues correctly | Open archive; check ordering and pagination | Not Tested | On track | 63
7 | P4-07 | Issue Archive | Year & decade filtering | P1 | Not Started | 2026-10-21 | 2026-10-21 | 0% | P4-06 | ⏳ 1 open | archive-magazine_issue.php, assets/js/modules/issue-filter.js | Filters return correct issues | Filter each decade/year; counts match manifest | Not Tested | On track | 64
8 | P4-08 | Single Issue | Single issue page | P0 | Not Started | 2026-10-22 | 2026-10-22 | 0% | P4-02 | ⏳ 1 open | single-magazine_issue.php | Single issue page complete for every issue | Open 5 issues incl. oldest and newest | Not Tested | On track | 65
9 | P4-09 | Flipbook | Flipbook reader | P1 | Not Started | 2026-10-22 | 2026-10-22 | 0% | P4-08 | ⏳ 1 open | assets/js/modules/flipbook.js, assets/vendor/pdfjs/* | Readable flipbook on desktop & mobile without blocking page load | Open large PDF on mobile & desktop; measure load time | Not Tested | On track | 66
10 | P4-10 | PDF Downloads | Secure PDF downloads | P0 | Not Started | 2026-10-22 | 2026-10-22 | 0% | P4-08 | ⏳ 1 open | inc/pdf-download.php | Downloads work and respect access rules | Download as guest/member/subscriber; check headers | Not Tested | On track | 67
11 | P4-11 | Access Control | Issue access restrictions | P0 | Not Started | 2026-10-22 | 2026-10-22 | 0% | P4-10, P5-07 | ⏳ 2 open | inc/pdf-download.php, .htaccess | Restricted PDFs cannot be accessed without entitlement | Try direct PDF URL logged-out; test each tier | Not Tested | External req. | 68
12 | P4-12 | Phase QA | Verify all 48 issues | P0 | Not Started | 2026-10-22 | 2026-10-22 | 0% | P4-04, P4-07, P4-09 | ⏳ 3 open | issues-manifest.csv | 48/48 issues verified | Tick all 48 against manifest | Not Tested | On track | 69
13
14
15
16
17
18
19
20

## P5 Auth Subs AdOps
PHASE 5 — AUTH, SUBSCRIPTIONS, ADOPS & LEADS
Window 23 Oct – 25 Oct 2026 · Status is read live from the Master Tracker (edit there)
← Dashboard |  |  | Open Master Tracker → |  | Staging ↗
COMPLETION |  |  | PLANNED | TASKS |  | DONE | IN PROGRESS |  | BLOCKED |  | OVERDUE | IN REVIEW / TEST | OPEN P0 | DEADLINE | PHASE STATUS
0% |  |  | 0% | 20 |  | 0 | 0 |  | 0 |  | 0 | 0 | 11 | 2026-10-25 | Not Started
Progress ░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░ 0% (planned 0%)
PHASE GOAL
Enable reader accounts (email, Google, Apple), paid subscription tiers with verified payment webhooks, a member dashboard, and revenue pages (advertising, rate calculator, media kit, lead capture) plus About/Contact and editorial role permissions — all hardened against abuse.
DELIVERABLES | [8 empty] | REQUIRED WORDPRESS FILES
▸ Login, registration, password reset | [8 empty] | ▸ page-templates/page-login.php, page-register.php, page-reset.php
▸ Google and Apple sign-in | [8 empty] | ▸ page-templates/page-account.php
▸ Member dashboard | [8 empty] | ▸ inc/auth/*.php
▸ Security hardening & rate limiting | [8 empty] | ▸ inc/auth/social-google.php, social-apple.php
▸ Subscription tiers + payment gateway + verified webhooks | [8 empty] | ▸ inc/subscriptions/*.php
▸ Advertising page, rate calculator, media kit | [8 empty] | ▸ inc/payments/gateway.php, webhook.php
▸ Lead capture forms | [8 empty] | ▸ page-templates/page-advertise.php
▸ About and Contact pages | [8 empty] | ▸ assets/js/modules/rate-calculator.js
▸ Editorial roles & permissions | [8 empty] | ▸ inc/leads.php
▸ page-templates/page-about.php, page-contact.php
▸ inc/roles.php
▸ inc/security.php
TECHNICAL IMPLEMENTATION STEPS
1 | Day 1: request Google OAuth, Apple Developer and payment-provider credentials
2 | Build custom auth templates (wp_signon, registration, reset, email verification)
3 | Integrate Google OAuth 2.0 and Sign in with Apple
4 | Model tiers (roles/capabilities + user meta expiry)
5 | Integrate gateway hosted checkout (sandbox first)
6 | Implement webhook endpoint with signature check + idempotency
7 | Build member dashboard (profile, plan, downloads)
8 | Add rate limiting, nonces, CAPTCHA/honeypot
9 | Build advertising page, calculator, media kit, lead forms (stored + emailed)
10 | Build About/Contact; configure SMTP; define editorial roles
DETAILED TASK CHECKLIST (live from Master Tracker — change Status / % there)
# | Task ID | Module | Task | Priority | Status | Start | Due | Complete | Dependencies | Dep. check | WordPress files | Acceptance criteria | Testing checklist | Test result | Alert
1 | P5-01 | Credentials | Request Google OAuth credentials | P1 | Not Started | 2026-10-12 | 2026-10-20 | 0% |  |  | — | Valid client ID/secret for both domains | Credentials received and stored securely (not in Git) | Not Tested | External req. | 70
2 | P5-02 | Credentials | Request Sign in with Apple credentials | P1 | Not Started | 2026-10-12 | 2026-10-20 | 0% |  |  | — | Valid Apple credentials for both domains | Credentials received; domain verification file placed | Not Tested | External req. | 71
3 | P5-03 | Payments | Confirm payment provider & obtain API keys | P0 | Not Started | 2026-10-12 | 2026-10-22 | 0% |  |  | — | Sandbox keys in hand; live approval confirmed before cutover | Sandbox transaction possible; live approval date known | Not Tested | External req. | 72
4 | P5-04 | Authentication | Login, registration & password reset | P0 | Not Started | 2026-10-23 | 2026-10-23 | 0% | P1-17 | ⏳ 1 open | page-templates/page-login.php, page-register.php, page-reset.php, inc/auth/*.php | Complete account lifecycle works with clear Arabic messages | Register, verify, log in, reset password, log out | Not Tested | On track | 73
5 | P5-05 | Authentication | Google sign-in | P1 | Not Started | 2026-10-23 | 2026-10-23 | 0% | P5-01, P5-04 | ⏳ 2 open | inc/auth/social-google.php | Google sign-in works on staging and is ready for production URIs | New and existing user sign-in; cancel flow | Not Tested | External req. | 74
6 | P5-06 | Authentication | Sign in with Apple | P2 | Not Started | 2026-10-23 | 2026-10-23 | 0% | P5-02, P5-04 | ⏳ 2 open | inc/auth/social-apple.php | Apple sign-in works including private relay emails | Sign in on Safari iOS & desktop; hide-my-email case | Not Tested | External req. | 75
7 | P5-07 | Subscriptions | Subscription tiers model | P0 | Not Started | 2026-10-23 | 2026-10-23 | 0% | P5-04 | ⏳ 1 open | inc/subscriptions/tiers.php, page-templates/page-subscribe.php | Tiers control access across issues and content | Assign each tier manually; check entitlements | Not Tested | On track | 76
8 | P5-08 | Payments | Payment gateway checkout integration | P0 | Not Started | 2026-10-23 | 2026-10-24 | 0% | P5-03, P5-07 | ⏳ 2 open | inc/payments/gateway.php | Paid checkout activates correct tier in sandbox | Sandbox: success, decline, cancel | Not Tested | External req. | 77
9 | P5-09 | Payments | Payment webhooks | P0 | Not Started | 2026-10-24 | 2026-10-24 | 0% | P5-08 | ⏳ 1 open | inc/payments/webhook.php | Subscription state always matches gateway; duplicates ignored | Replay same event twice; tampered signature rejected | Not Tested | External req. | 78
10 | P5-10 | Subscriptions | Renewal, expiry & notification emails | P1 | Not Started | 2026-10-24 | 2026-10-24 | 0% | P5-09, P5-13 | ⏳ 2 open | inc/subscriptions/cron.php | Expired users lose access; reminders sent | Force-expire a test user; check emails | Not Tested | On track | 79
11 | P5-11 | Member Dashboard | Member dashboard | P0 | Not Started | 2026-10-24 | 2026-10-24 | 0% | P5-04, P5-07 | ⏳ 2 open | page-templates/page-account.php | Members manage account and see entitlements | Check as free, member and subscriber | Not Tested | On track | 80
12 | P5-12 | Security | Security hardening & rate limiting | P0 | Not Started | 2026-10-24 | 2026-10-24 | 0% | P5-04 | ⏳ 1 open | inc/security.php | Abuse throttled; no user enumeration; forms CSRF-safe | Brute-force 10 attempts → lockout; CSRF test without nonce | Not Tested | On track | 81
13 | P5-13 | Email | SMTP / transactional email setup | P0 | Not Started | 2026-10-24 | 2026-10-25 | 0% |  |  | wp-config.php or SMTP plugin settings | Transactional emails delivered to inbox | Send test emails to Gmail/Outlook; check spam | Not Tested | External req. | 82
14 | P5-14 | AdOps | Advertising page | P1 | Not Started | 2026-10-25 | 2026-10-25 | 0% | P1-17 | ⏳ 1 open | page-templates/page-advertise.php | Advertising page live with editable content | Content review with client; responsive check | Not Tested | External req. | 83
15 | P5-15 | AdOps | Advertising rate calculator | P1 | Not Started | 2026-10-25 | 2026-10-25 | 0% | P5-14 | ⏳ 1 open | assets/js/modules/rate-calculator.js, inc/adops-settings.php | Calculator accurate and admin-configurable | Test edge values; change a rate in admin | Not Tested | External req. | 84
16 | P5-16 | AdOps | Media kit download | P2 | Not Started | 2026-10-25 | 2026-10-25 | 0% | P5-14, P5-17 | ⏳ 2 open | page-templates/page-advertise.php | Media kit downloadable and tracked | Download after form submit | Not Tested | External req. | 85
17 | P5-17 | Leads | Lead capture forms | P0 | Not Started | 2026-10-25 | 2026-10-25 | 0% | P5-12, P5-13 | ⏳ 2 open | inc/leads.php | Every lead stored and notified; spam blocked | Submit valid/invalid/spam; export CSV | Not Tested | On track | 86
18 | P5-18 | Pages | About page | P1 | Not Started | 2026-10-25 | 2026-10-25 | 0% | P1-17 | ⏳ 1 open | page-templates/page-about.php | About page live and editable | Content review; responsive check | Not Tested | External req. | 87
19 | P5-19 | Pages | Contact page | P0 | Not Started | 2026-10-25 | 2026-10-25 | 0% | P5-17 | ⏳ 1 open | page-templates/page-contact.php | Contact form works end-to-end | Submit form; check stored entry and email | Not Tested | On track | 88
20 | P5-20 | Roles | Editorial roles & permissions | P0 | Not Started | 2026-10-25 | 2026-10-25 | 0% | P2-02 | ⏳ 1 open | inc/roles.php | Each role can do exactly what it needs and nothing more | Log in as each role; attempt forbidden actions | Not Tested | On track | 89
21
22
23
24
25
26
27
28

## P6 Cleanup & Cutover
PHASE 6 — DATABASE CLEANUP, CRAWL AUDIT & CUTOVER
Window 26 Oct – 31 Oct 2026 · Status is read live from the Master Tracker (edit there)
← Dashboard |  |  | Open Master Tracker → |  | Staging ↗
COMPLETION |  |  | PLANNED | TASKS |  | DONE | IN PROGRESS |  | BLOCKED |  | OVERDUE | IN REVIEW / TEST | OPEN P0 | DEADLINE | PHASE STATUS
0% |  |  | 0% | 22 |  | 0 | 0 |  | 0 |  | 0 | 0 | 20 | 2026-11-01 | Not Started
Progress ░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░░ 0% (planned 0%)
PHASE GOAL
Protect data and search equity: back up and audit the database, remove legacy JNews dependencies safely, prove all 2,645 article URLs and SEO metadata survive, optimize performance with LiteSpeed, complete security and cross-browser testing, and execute a rehearsed, reversible production cutover on 1 November.
DELIVERABLES | [8 empty] | REQUIRED WORDPRESS FILES
▸ Verified full backups (files + DB) before work and before cutover | [8 empty] | ▸ wp-config.php
▸ Database audit and JNews dependency report | [8 empty] | ▸ .htaccess
▸ Safe database optimization (staging first) | [8 empty] | ▸ LiteSpeed Cache settings export
▸ URL inventory + validation of 2,645 article URLs | [8 empty] | ▸ inc/redirects.php (or Redirection plugin export)
▸ SEO baseline vs. staging comparison + redirect map | [8 empty] | ▸ url-inventory.csv
▸ Performance optimization + LiteSpeed configuration | [8 empty] | ▸ seo-baseline.csv
▸ Responsive, cross-browser and security verification | [8 empty] | ▸ backups/ (off-server)
▸ Deployment readiness sign-off and rehearsed rollback plan | [8 empty] | ▸ deployment-runbook (this workbook, sheet 11)
▸ Production cutover and post-launch verification
TECHNICAL IMPLEMENTATION STEPS
1 | Day 1: full production backup (files + DB), stored off-server, restore-tested
2 | Day 2: DB audit, JNews dependency review, URL inventory & SEO baseline
3 | Optimize DB on staging only (revisions, transients, orphan meta, autoload)
4 | Crawl staging; compare status codes, titles, metas, canonicals vs baseline
5 | Build 301 map for any changed URLs
6 | Tune Core Web Vitals; configure LiteSpeed (exclude account/checkout)
7 | Run QA & Testing sheet; fix defects in buffer
8 | Security verification (headers, enumeration, XML-RPC, permissions)
9 | Client UAT sign-off; rehearse rollback on staging
10 | 1 Nov: fresh backup → cutover → purge caches → smoke test → monitor
DETAILED TASK CHECKLIST (live from Master Tracker — change Status / % there)
# | Task ID | Module | Task | Priority | Status | Start | Due | Complete | Dependencies | Dep. check | WordPress files | Acceptance criteria | Testing checklist | Test result | Alert
1 | P6-01 | Backup | Full production backup (files + DB) before any work | P0 | Not Started | 2026-10-12 | 2026-10-12 | 0% |  |  | backups/ (off-server) | Restorable backup exists before any change | Checksum verified; DB dump imports cleanly on staging | Not Tested | Due soon | 90
2 | P6-02 | Backup | Verify staging mirrors production | P0 | Not Started | 2026-10-12 | 2026-10-12 | 0% | P6-01 | ⏳ 1 open | wp-config.php, database | Staging is a verified mirror; content-delta plan agreed | Compare post/term/user counts staging vs production | Not Tested | Due soon | 91
3 | P6-03 | DB Audit | Database audit | P0 | Not Started | 2026-10-13 | 2026-10-13 | 0% | P6-02 | ⏳ 1 open | database (phpMyAdmin) | Audit report saved; risks logged | Run audit queries; export results | Not Tested | Due soon | 92
4 | P6-04 | JNews Review | Legacy JNews dependency review | P0 | Not Started | 2026-10-13 | 2026-10-13 | 0% | P6-03 | ⏳ 1 open | database, wp-content/plugins/jnews-* | Every JNews dependency has a documented decision | SQL LIKE search for shortcodes; meta key frequency list | Not Tested | Due soon | 93
5 | P6-05 | URL Inventory | Export URL inventory (2,645 articles + taxonomies) | P0 | Not Started | 2026-10-13 | 2026-10-13 | 0% | P6-01 | ⏳ 1 open | url-inventory.csv | Complete URL inventory saved | Row count = 2,645 articles + taxonomy/page rows | Not Tested | Due soon | 94
6 | P6-06 | SEO Baseline | Capture SEO baseline | P0 | Not Started | 2026-10-13 | 2026-10-13 | 0% | P6-05 | ⏳ 1 open | seo-baseline.csv | Baseline available for comparison | Baseline crawl complete; GSC export saved | Not Tested | Due soon | 95
7 | P6-07 | DB Optimization | Safe database optimization (staging first) | P1 | Not Started | 2026-10-26 | 2026-10-26 | 0% | P6-03, P6-04 | ⏳ 2 open | wp-config.php (WP_POST_REVISIONS), database | DB smaller and faster with no content loss | Before/after sizes; site regression check | Not Tested | On track | 96
8 | P6-08 | URL Validation | Validate all 2,645 article URLs on staging | P0 | Not Started | 2026-10-26 | 2026-10-26 | 0% | P6-05, P3-16 | ⏳ 2 open | url-inventory.csv | 2,645/2,645 article URLs return 200 with correct content | Automated crawl; 0 unexpected 404s | Not Tested | On track | 97
9 | P6-09 | SEO | SEO comparison: staging vs baseline | P0 | Not Started | 2026-10-26 | 2026-10-27 | 0% | P6-06, P6-08 | ⏳ 2 open | seo-baseline.csv | No SEO regressions vs baseline | Diff report reviewed | Not Tested | On track | 98
10 | P6-10 | SEO | 301 redirect map for changed URLs | P1 | Not Started | 2026-10-27 | 2026-10-27 | 0% | P6-08 | ⏳ 1 open | inc/redirects.php or Redirection export | All changed URLs 301 to correct targets; no chains | .htaccess / plugin test of each mapping | Not Tested | On track | 99
11 | P6-11 | Performance | Performance optimization (Core Web Vitals) | P0 | Not Started | 2026-10-27 | 2026-10-28 | 0% | P2-24, P3-16, P4-12 | ⏳ 3 open | inc/enqueue.php, assets/* | Key templates meet Core Web Vitals targets on mobile | Lighthouse/PageSpeed on homepage, article, category, issue | Not Tested | On track | 100
12 | P6-12 | Caching | LiteSpeed Cache configuration | P0 | Not Started | 2026-10-28 | 2026-10-28 | 0% | P6-11, P2-08 | ⏳ 2 open | LiteSpeed Cache settings | Fast cached pages with no cached private content | Logged-in vs guest caching; checkout not cached; purge on publish | Not Tested | External req. | 101
13 | P6-13 | Testing | Responsive testing | P0 | Not Started | 2026-10-28 | 2026-10-28 | 0% | P6-11 | ⏳ 1 open | — | All templates pass responsive checks | QA sheet: Mobile Responsiveness rows | Not Tested | On track | 102
14 | P6-14 | Testing | Cross-browser testing | P0 | Not Started | 2026-10-28 | 2026-10-29 | 0% | P6-13 | ⏳ 1 open | — | No blocking issues in supported browsers | QA sheet: Browser Compatibility rows | Not Tested | On track | 103
15 | P6-15 | Security | Security verification | P0 | Not Started | 2026-10-29 | 2026-10-29 | 0% | P5-12 | ⏳ 1 open | wp-config.php, .htaccess | No high-severity findings open | QA sheet: Security rows; header scan | Not Tested | External req. | 104
16 | P6-16 | Testing | Full QA regression run | P0 | Not Started | 2026-10-29 | 2026-10-30 | 0% | P6-13, P6-14 | ⏳ 2 open | — | All P0 test cases pass | QA sheet completion = 100% | Not Tested | On track | 105
17 | P6-17 | Bug Fixing | Defect fixing buffer | P0 | Not Started | 2026-10-30 | 2026-10-31 | 0% | P6-16 | ⏳ 1 open | — | No open P0/P1 defects | Re-test fixed defects | Not Tested | On track | 106
18 | P6-18 | Readiness | Deployment readiness review & client UAT sign-off | P0 | Not Started | 2026-10-31 | 2026-10-31 | 0% | P6-17 | ⏳ 1 open | — | Written client approval to deploy | Deployment sheet stage 1 complete | Not Tested | On track | 107
19 | P6-19 | Rollback | Rollback plan documented & rehearsed | P0 | Not Started | 2026-10-31 | 2026-10-31 | 0% | P6-01 | ⏳ 1 open | Deployment & Rollback sheet | Rollback achievable within agreed window (target < 30 min) | Timed rehearsal | Not Tested | External req. | 108
20 | P6-20 | Backup | Fresh pre-cutover production backup | P0 | Not Started | 2026-10-31 | 2026-10-31 | 0% | P6-18 | ⏳ 1 open | backups/ (off-server) | Verified backup timestamped before cutover | Checksum + test import | Not Tested | External req. | 109
21 | P6-21 | Cutover | Production cutover | P0 | Not Started | 2026-11-01 | 2026-11-01 | 0% | P6-18, P6-19, P6-20 | ⏳ 3 open | theme package, settings exports | New site live on production with no data loss | Follow Deployment sheet stages 5–7 | Not Tested | External req. | 110
22 | P6-22 | Post-launch | Post-launch verification & monitoring | P0 | Not Started | 2026-11-01 | 2026-11-01 | 0% | P6-21 | ⏳ 1 open | debug.log, Search Console | No critical issues in first 48 h | Deployment sheet stage 8–9 | Not Tested | On track | 111
23
24
25
26
27
28
29
30

## QA & Testing
QA & TESTING CHECKLISTS
Run on staging. Set Result from the dropdown; summary and pass rates update automatically.
← Dashboard |  | Staging ↗
| Area | Cases | Pass | Fail | Blocked | Not Run | Pass rate
| Template 1: Homepage | 3 | 0 | 0 | 0 | 3 | 0%
| Template 2: Single Article | 3 | 0 | 0 | 0 | 3 | 0%
| Template 3: Category Archive | 3 | 0 | 0 | 0 | 3 | 0%
| Template 4: Author Profile | 3 | 0 | 0 | 0 | 3 | 0%
| Template 5: Issues Archive | 3 | 0 | 0 | 0 | 3 | 0%
| Template 6: Single Issue | 3 | 0 | 0 | 0 | 3 | 0%
| Template 7: Advertise | 3 | 0 | 0 | 0 | 3 | 0%
| Template 8: About | 3 | 0 | 0 | 0 | 3 | 0%
| Template 9: Contact | 3 | 0 | 0 | 0 | 3 | 0%
| WordPress Dynamic Content | 8 | 0 | 0 | 0 | 8 | 0%
| RTL Layout | 5 | 0 | 0 | 0 | 5 | 0%
| Mobile Responsiveness | 6 | 0 | 0 | 0 | 6 | 0%
| Authentication | 8 | 0 | 0 | 0 | 8 | 0%
| Subscription Functionality | 5 | 0 | 0 | 0 | 5 | 0%
| Payment Workflows | 7 | 0 | 0 | 0 | 7 | 0%
| SEO Metadata | 8 | 0 | 0 | 0 | 8 | 0%
| Existing Article URLs | 5 | 0 | 0 | 0 | 5 | 0%
| Performance | 6 | 0 | 0 | 0 | 6 | 0%
| Security | 8 | 0 | 0 | 0 | 8 | 0%
| Contact Forms | 5 | 0 | 0 | 0 | 5 | 0%
| Magazine PDFs | 6 | 0 | 0 | 0 | 6 | 0%
| Browser Compatibility | 6 | 0 | 0 | 0 | 6 | 0%
| TOTAL | 110 | 0 | 0 | 0 | 110 | 0%
QA ID | Area | Test Case | Expected Result | Page / URL | Device / Browser | Priority | Linked Task | Result | Tested On | Defect / Notes
QA-001 | Template 1: Homepage | Homepage renders with correct template | Correct template file (Query Monitor), header/footer present, no PHP notices | / | Desktop Chrome | P0 | P2-24 | Not Run
QA-002 | Template 1: Homepage | Homepage shows live WordPress content | All content pulled dynamically; editing in admin updates page after cache purge | / | Desktop Chrome | P0 | P2-24 | Not Run
QA-003 | Template 1: Homepage | Homepage responsive & RTL | Layout correct at 360/768/1440 px, RTL alignment, no horizontal scroll | / | iPhone + Android + Desktop | P0 | P2-24 | Not Run
QA-004 | Template 2: Single Article | Single Article renders with correct template | Correct template file (Query Monitor), header/footer present, no PHP notices | /<sample-article>/ | Desktop Chrome | P0 | P3-01 | Not Run
QA-005 | Template 2: Single Article | Single Article shows live WordPress content | All content pulled dynamically; editing in admin updates page after cache purge | /<sample-article>/ | Desktop Chrome | P0 | P3-01 | Not Run
QA-006 | Template 2: Single Article | Single Article responsive & RTL | Layout correct at 360/768/1440 px, RTL alignment, no horizontal scroll | /<sample-article>/ | iPhone + Android + Desktop | P0 | P3-01 | Not Run
QA-007 | Template 3: Category Archive | Category Archive renders with correct template | Correct template file (Query Monitor), header/footer present, no PHP notices | /category/<slug>/ | Desktop Chrome | P0 | P3-09 | Not Run
QA-008 | Template 3: Category Archive | Category Archive shows live WordPress content | All content pulled dynamically; editing in admin updates page after cache purge | /category/<slug>/ | Desktop Chrome | P0 | P3-09 | Not Run
QA-009 | Template 3: Category Archive | Category Archive responsive & RTL | Layout correct at 360/768/1440 px, RTL alignment, no horizontal scroll | /category/<slug>/ | iPhone + Android + Desktop | P0 | P3-09 | Not Run
QA-010 | Template 4: Author Profile | Author Profile renders with correct template | Correct template file (Query Monitor), header/footer present, no PHP notices | /author/<slug>/ | Desktop Chrome | P0 | P3-08 | Not Run
QA-011 | Template 4: Author Profile | Author Profile shows live WordPress content | All content pulled dynamically; editing in admin updates page after cache purge | /author/<slug>/ | Desktop Chrome | P0 | P3-08 | Not Run
QA-012 | Template 4: Author Profile | Author Profile responsive & RTL | Layout correct at 360/768/1440 px, RTL alignment, no horizontal scroll | /author/<slug>/ | iPhone + Android + Desktop | P0 | P3-08 | Not Run
QA-013 | Template 5: Issues Archive | Issues Archive renders with correct template | Correct template file (Query Monitor), header/footer present, no PHP notices | /issues/ | Desktop Chrome | P0 | P4-06 | Not Run
QA-014 | Template 5: Issues Archive | Issues Archive shows live WordPress content | All content pulled dynamically; editing in admin updates page after cache purge | /issues/ | Desktop Chrome | P0 | P4-06 | Not Run
QA-015 | Template 5: Issues Archive | Issues Archive responsive & RTL | Layout correct at 360/768/1440 px, RTL alignment, no horizontal scroll | /issues/ | iPhone + Android + Desktop | P0 | P4-06 | Not Run
QA-016 | Template 6: Single Issue | Single Issue renders with correct template | Correct template file (Query Monitor), header/footer present, no PHP notices | /issues/<issue>/ | Desktop Chrome | P0 | P4-08 | Not Run
QA-017 | Template 6: Single Issue | Single Issue shows live WordPress content | All content pulled dynamically; editing in admin updates page after cache purge | /issues/<issue>/ | Desktop Chrome | P0 | P4-08 | Not Run
QA-018 | Template 6: Single Issue | Single Issue responsive & RTL | Layout correct at 360/768/1440 px, RTL alignment, no horizontal scroll | /issues/<issue>/ | iPhone + Android + Desktop | P0 | P4-08 | Not Run
QA-019 | Template 7: Advertise | Advertise renders with correct template | Correct template file (Query Monitor), header/footer present, no PHP notices | /advertise/ | Desktop Chrome | P0 | P5-14 | Not Run
QA-020 | Template 7: Advertise | Advertise shows live WordPress content | All content pulled dynamically; editing in admin updates page after cache purge | /advertise/ | Desktop Chrome | P0 | P5-14 | Not Run
QA-021 | Template 7: Advertise | Advertise responsive & RTL | Layout correct at 360/768/1440 px, RTL alignment, no horizontal scroll | /advertise/ | iPhone + Android + Desktop | P0 | P5-14 | Not Run
QA-022 | Template 8: About | About renders with correct template | Correct template file (Query Monitor), header/footer present, no PHP notices | /about/ | Desktop Chrome | P0 | P5-18 | Not Run
QA-023 | Template 8: About | About shows live WordPress content | All content pulled dynamically; editing in admin updates page after cache purge | /about/ | Desktop Chrome | P0 | P5-18 | Not Run
QA-024 | Template 8: About | About responsive & RTL | Layout correct at 360/768/1440 px, RTL alignment, no horizontal scroll | /about/ | iPhone + Android + Desktop | P0 | P5-18 | Not Run
QA-025 | Template 9: Contact | Contact renders with correct template | Correct template file (Query Monitor), header/footer present, no PHP notices | /contact/ | Desktop Chrome | P0 | P5-19 | Not Run
QA-026 | Template 9: Contact | Contact shows live WordPress content | All content pulled dynamically; editing in admin updates page after cache purge | /contact/ | Desktop Chrome | P0 | P5-19 | Not Run
QA-027 | Template 9: Contact | Contact responsive & RTL | Layout correct at 360/768/1440 px, RTL alignment, no horizontal scroll | /contact/ | iPhone + Android + Desktop | P0 | P5-19 | Not Run
QA-028 | WordPress Dynamic Content | Section source change (category/tag) | Section shows posts from newly selected terms | / | Desktop Chrome | P0 | P2-03 | Not Run
QA-029 | WordPress Dynamic Content | Post count / order / offset | Output matches configured values exactly | / | Desktop Chrome | P0 | P2-04 | Not Run
QA-030 | WordPress Dynamic Content | Manual post selection | Pinned posts appear in chosen order | / | Desktop Chrome | P0 | P2-05 | Not Run
QA-031 | WordPress Dynamic Content | Layout switch | Each layout variant renders | / | Desktop Chrome | P0 | P2-06 | Not Run
QA-032 | WordPress Dynamic Content | Section hide / reorder | Hidden section gone; order updated; no duplicates | / | Desktop Chrome | P0 | P2-07 | Not Run
QA-033 | WordPress Dynamic Content | Publish new post | Appears in relevant sections after auto-purge | / | Desktop Chrome | P0 | P2-08 | Not Run
QA-034 | WordPress Dynamic Content | Breaking ticker source | Adding/removing breaking tag updates ticker | / | Desktop Chrome | P0 | P2-10 | Not Run
QA-035 | WordPress Dynamic Content | Most-read widget | Counts increment and tabs switch | / | Desktop Chrome | P0 | P2-22 | Not Run
QA-036 | RTL Layout | Document direction | <html dir='rtl' lang='ar'> on every template | All | Desktop + Mobile | P0 | P1-09 | Not Run
QA-037 | RTL Layout | Mixed Arabic/English text | Bidi isolation correct, punctuation in right place | All | Desktop + Mobile | P0 | P1-09 | Not Run
QA-038 | RTL Layout | Icons & arrows mirrored | Directional icons point correctly in RTL | All | Desktop + Mobile | P0 | P1-09 | Not Run
QA-039 | RTL Layout | Forms in RTL | Inputs, labels, errors aligned right | All | Desktop + Mobile | P0 | P1-09 | Not Run
QA-040 | RTL Layout | Ticker & sliders direction | Scroll/swipe direction natural for RTL | All | Desktop + Mobile | P0 | P1-09 | Not Run
QA-041 | Mobile Responsiveness | 360 px small phone | All templates usable, tap targets ≥ 44 px | All | iPhone Safari, Android Chrome | P0 | P6-13 | Not Run
QA-042 | Mobile Responsiveness | Mobile navigation drawer | Opens, closes, focus trapped, scroll locked | All | iPhone Safari, Android Chrome | P0 | P6-13 | Not Run
QA-043 | Mobile Responsiveness | Tablet 768–1024 px | Grids reflow correctly | All | iPhone Safari, Android Chrome | P0 | P6-13 | Not Run
QA-044 | Mobile Responsiveness | Images & covers | Correct srcset size served, no distortion | All | iPhone Safari, Android Chrome | P0 | P6-13 | Not Run
QA-045 | Mobile Responsiveness | Flipbook on mobile | Fallback reader usable | All | iPhone Safari, Android Chrome | P0 | P6-13 | Not Run
QA-046 | Mobile Responsiveness | Forms on mobile | Correct keyboard types, no zoom on focus | All | iPhone Safari, Android Chrome | P0 | P6-13 | Not Run
QA-047 | Authentication | Email registration + verification | Account created, verification email received, account activated | /login/, /register/, /account/ | Desktop + Mobile | P0 | P5-04 | Not Run
QA-048 | Authentication | Login / logout | Redirects correct, session cleared on logout | /login/, /register/, /account/ | Desktop + Mobile | P0 | P5-04 | Not Run
QA-049 | Authentication | Password reset | Reset email received; link expires; new password works | /login/, /register/, /account/ | Desktop + Mobile | P0 | P5-04 | Not Run
QA-050 | Authentication | Google sign-in | New & existing account linking works | /login/, /register/, /account/ | Desktop + Mobile | P0 | P5-05 | Not Run
QA-051 | Authentication | Apple sign-in | Works incl. private relay email | /login/, /register/, /account/ | Desktop + Mobile | P0 | P5-06 | Not Run
QA-052 | Authentication | Rate limiting | Lockout after repeated failures; generic error messages | /login/, /register/, /account/ | Desktop + Mobile | P0 | P5-12 | Not Run
QA-053 | Authentication | No user enumeration | Login/reset responses do not reveal whether user exists | /login/, /register/, /account/ | Desktop + Mobile | P0 | P5-12 | Not Run
QA-054 | Authentication | Member dashboard | Profile, plan, history, downloads visible | /login/, /register/, /account/ | Desktop + Mobile | P0 | P5-11 | Not Run
QA-055 | Subscription Functionality | Tier entitlements | Each tier accesses only its content/issues | /subscribe/, /account/ | Desktop | P0 | P5-07 | Not Run
QA-056 | Subscription Functionality | Upgrade | Upgrading changes entitlements immediately | /subscribe/, /account/ | Desktop | P0 | P5-07 | Not Run
QA-057 | Subscription Functionality | Expiry | Expired subscription loses access after grace period | /subscribe/, /account/ | Desktop | P0 | P5-07 | Not Run
QA-058 | Subscription Functionality | Renewal reminder | Reminder email sent before expiry | /subscribe/, /account/ | Desktop | P0 | P5-07 | Not Run
QA-059 | Subscription Functionality | Pricing page | Tiers and prices match admin config | /subscribe/, /account/ | Desktop | P0 | P5-07 | Not Run
QA-060 | Payment Workflows | Successful payment (sandbox) | Order recorded, tier activated, receipt emailed | /checkout/ | Desktop | P0 | P5-09 | Not Run
QA-061 | Payment Workflows | Declined payment | Clear error, no activation | /checkout/ | Desktop | P0 | P5-09 | Not Run
QA-062 | Payment Workflows | Cancelled checkout | Returns to site, no activation | /checkout/ | Desktop | P0 | P5-09 | Not Run
QA-063 | Payment Workflows | Webhook signature invalid | Request rejected and logged | /checkout/ | Desktop | P0 | P5-09 | Not Run
QA-064 | Payment Workflows | Duplicate webhook | Processed once (idempotent) | /checkout/ | Desktop | P0 | P5-09 | Not Run
QA-065 | Payment Workflows | Refund event | Access revoked/adjusted | /checkout/ | Desktop | P0 | P5-09 | Not Run
QA-066 | Payment Workflows | Live mode smoke test | One real low-value transaction succeeds post-cutover | /checkout/ | Desktop | P0 | P5-09 | Not Run
QA-067 | SEO Metadata | Title tags | Match baseline or approved improvements | All | Crawler | P0 | P6-09 | Not Run
QA-068 | SEO Metadata | Meta descriptions | Present and match baseline | All | Crawler | P0 | P6-09 | Not Run
QA-069 | SEO Metadata | Canonical URLs | Self-referencing, correct domain | All | Crawler | P0 | P6-09 | Not Run
QA-070 | SEO Metadata | Open Graph / Twitter cards | Image, title, description correct when shared | All | Crawler | P0 | P6-09 | Not Run
QA-071 | SEO Metadata | Structured data | NewsArticle valid in Rich Results Test | All | Crawler | P0 | P6-09 | Not Run
QA-072 | SEO Metadata | XML sitemaps | Include posts, categories, issues; exclude private pages | All | Crawler | P0 | P6-09 | Not Run
QA-073 | SEO Metadata | Robots / noindex | Production indexable; staging noindex removed only on production | All | Crawler | P0 | P6-09 | Not Run
QA-074 | SEO Metadata | Breadcrumbs | Correct hierarchy and schema | All | Crawler | P0 | P6-09 | Not Run
QA-075 | Existing Article URLs | All 2,645 article URLs | 200 status, same permalink as production | url-inventory.csv | Crawler | P0 | P6-08 | Not Run
QA-076 | Existing Article URLs | Category & tag URLs | 200 status, same slugs | url-inventory.csv | Crawler | P0 | P6-08 | Not Run
QA-077 | Existing Article URLs | Author URLs | 200 status | url-inventory.csv | Crawler | P0 | P6-08 | Not Run
QA-078 | Existing Article URLs | Changed URLs | 301 to correct target, no chains | url-inventory.csv | Crawler | P0 | P6-08 | Not Run
QA-079 | Existing Article URLs | Internal links | No links to 404 pages | url-inventory.csv | Crawler | P0 | P6-08 | Not Run
QA-080 | Performance | Homepage LCP (mobile) | < 2.5 s | /, article, category, issue | PageSpeed Insights mobile | P0 | P6-11 | Not Run
QA-081 | Performance | Article LCP (mobile) | < 2.5 s | /, article, category, issue | PageSpeed Insights mobile | P0 | P6-11 | Not Run
QA-082 | Performance | CLS all templates | < 0.1 | /, article, category, issue | PageSpeed Insights mobile | P0 | P6-11 | Not Run
QA-083 | Performance | INP | < 200 ms | /, article, category, issue | PageSpeed Insights mobile | P0 | P6-11 | Not Run
QA-084 | Performance | Homepage DB queries (warm cache) | ≤ 40 queries | /, article, category, issue | PageSpeed Insights mobile | P0 | P6-11 | Not Run
QA-085 | Performance | LiteSpeed page cache | Guest pages served from cache; private pages not cached | /, article, category, issue | PageSpeed Insights mobile | P0 | P6-11 | Not Run
QA-086 | Security | Security headers | HSTS, X-Content-Type-Options, Referrer-Policy, frame options present | All | Desktop | P0 | P6-15 | Not Run
QA-087 | Security | File editing disabled | DISALLOW_FILE_EDIT true | All | Desktop | P0 | P6-15 | Not Run
QA-088 | Security | XML-RPC | Disabled or restricted | All | Desktop | P0 | P6-15 | Not Run
QA-089 | Security | REST user enumeration | /wp-json/wp/v2/users not exposing usernames publicly | All | Desktop | P0 | P6-15 | Not Run
QA-090 | Security | Form CSRF | All forms reject missing/invalid nonce | All | Desktop | P0 | P6-15 | Not Run
QA-091 | Security | Output escaping | No XSS with test payloads in search, forms | All | Desktop | P0 | P6-15 | Not Run
QA-092 | Security | Protected PDFs | Direct URL blocked for unentitled users | All | Desktop | P0 | P6-15 | Not Run
QA-093 | Security | Admin accounts | Only required admins; strong passwords; 2FA where possible | All | Desktop | P0 | P6-15 | Not Run
QA-094 | Contact Forms | Contact form valid submit | Stored + email received | /contact/, /advertise/ | Desktop + Mobile | P0 | P5-17 | Not Run
QA-095 | Contact Forms | Validation errors | Arabic messages; data preserved | /contact/, /advertise/ | Desktop + Mobile | P0 | P5-17 | Not Run
QA-096 | Contact Forms | Spam submission | Blocked by honeypot/CAPTCHA | /contact/, /advertise/ | Desktop + Mobile | P0 | P5-17 | Not Run
QA-097 | Contact Forms | Advertising lead form | Stored in leads, notification sent | /contact/, /advertise/ | Desktop + Mobile | P0 | P5-17 | Not Run
QA-098 | Contact Forms | Lead CSV export | Export opens with Arabic text intact (UTF-8) | /contact/, /advertise/ | Desktop + Mobile | P0 | P5-17 | Not Run
QA-099 | Magazine PDFs | 48 issues present | 48/48 in archive | /issues/ | Desktop + Mobile | P0 | P4-12 | Not Run
QA-100 | Magazine PDFs | Every PDF opens | No broken/corrupt files | /issues/ | Desktop + Mobile | P0 | P4-12 | Not Run
QA-101 | Magazine PDFs | Flipbook load | First page < 3 s on 4G | /issues/ | Desktop + Mobile | P0 | P4-12 | Not Run
QA-102 | Magazine PDFs | Download filenames | Meaningful names, correct headers | /issues/ | Desktop + Mobile | P0 | P4-12 | Not Run
QA-103 | Magazine PDFs | Access restriction | Gated issues blocked for guests | /issues/ | Desktop + Mobile | P0 | P4-12 | Not Run
QA-104 | Magazine PDFs | Year/decade filters | Counts match manifest | /issues/ | Desktop + Mobile | P0 | P4-12 | Not Run
QA-105 | Browser Compatibility | Core journeys in Chrome (latest, Windows/macOS) | Homepage, article, archive, issue reader, login and checkout work without visual/functional defects | All | Chrome (latest, Windows/macOS) | P0 | P6-14 | Not Run
QA-106 | Browser Compatibility | Core journeys in Safari (macOS) | Homepage, article, archive, issue reader, login and checkout work without visual/functional defects | All | Safari (macOS) | P0 | P6-14 | Not Run
QA-107 | Browser Compatibility | Core journeys in Safari (iOS) | Homepage, article, archive, issue reader, login and checkout work without visual/functional defects | All | Safari (iOS) | P0 | P6-14 | Not Run
QA-108 | Browser Compatibility | Core journeys in Firefox (latest) | Homepage, article, archive, issue reader, login and checkout work without visual/functional defects | All | Firefox (latest) | P0 | P6-14 | Not Run
QA-109 | Browser Compatibility | Core journeys in Edge (latest) | Homepage, article, archive, issue reader, login and checkout work without visual/functional defects | All | Edge (latest) | P0 | P6-14 | Not Run
QA-110 | Browser Compatibility | Core journeys in Samsung Internet (Android) | Homepage, article, archive, issue reader, login and checkout work without visual/functional defects | All | Samsung Internet (Android) | P0 | P6-14 | Not Run

## Deployment & Rollback
DEPLOYMENT & ROLLBACK RUNBOOK · Cutover 1 Nov 2026
Production stays untouched until every Stage 1 item is Done and the client has approved deployment.
← Dashboard |  | Production ↗ | Readiness: 0% · Failed steps: 0
Step | Stage | Action | Verification | Tool / Location | Owner | Status | Done At | Notes
1 | 1. Staging Verification | All P0 tasks Completed in Master Tracker | Dashboard shows 0 open P0 tasks and 0 blocked | Dashboard | Developer | Not Started
2 | 1. Staging Verification | QA & Testing: all P0 cases Pass | QA summary pass rate for P0 = 100% | QA sheet | Developer | Not Started
3 | 1. Staging Verification | Client UAT written approval received | Email/document archived (P6-18) | Approval email | Developer | Not Started
4 | 1. Staging Verification | Live payment keys & production OAuth redirect URIs confirmed | Gateway live mode approved; Google/Apple allow production domain | Provider dashboards | Developer | Not Started
5 | 1. Staging Verification | Announce content freeze window to editors | Editors confirm no publishing during cutover | Email | Developer | Not Started
6 | 2. Full Backup | Full production files backup (incl. uploads) | Archive size & checksum recorded; stored off-server | hPanel / SSH | Developer | Not Started
7 | 2. Full Backup | Export current theme, plugin list & settings | JNews theme + plugin versions recorded | WP admin | Developer | Not Started
8 | 2. Full Backup | Export Customizer/widgets/menus from production | Export files saved | WP admin | Developer | Not Started
9 | 3. Database Backup | Full production DB dump | Dump imports cleanly into scratch DB | phpMyAdmin / mysqldump | Developer | Not Started
10 | 3. Database Backup | Record row counts (posts 2,645 articles, users, terms) | Counts saved for post-launch comparison | SQL | Developer | Not Started
11 | 4. SEO Comparison | Final staging crawl vs baseline | No unexpected title/meta/canonical differences | Crawler | Developer | Not Started
12 | 4. SEO Comparison | Redirect map loaded and tested | All mapped URLs 301 correctly | Redirect tool | Developer | Not Started
13 | 4. SEO Comparison | Confirm production will stay indexable | Search engine visibility setting ON in production; staging noindex not migrated | WP admin | Developer | Not Started
14 | 5. Theme Activation | Enable maintenance mode (short) | Visitors see maintenance page; admins can access | Maintenance plugin | Developer | Not Started
15 | 5. Theme Activation | Upload theme package to production | Files match tagged Git release | SFTP / Git | Developer | Not Started
16 | 5. Theme Activation | Install/activate required plugins & settings | Plugin list matches staging | WP admin | Developer | Not Started
17 | 5. Theme Activation | Migrate magazine issues (48), leads config, roles, Customizer settings | 48 issues present; homepage sections configured | Import tools | Developer | Not Started
18 | 5. Theme Activation | Run approved DB optimizations | Only steps rehearsed on staging executed | SQL / plugin | Developer | Not Started
19 | 5. Theme Activation | Activate theme 'altijara' | Homepage renders new theme | WP admin | Developer | Not Started
20 | 5. Theme Activation | Switch credentials/webhooks to production (payments, OAuth, SMTP) | Webhook endpoint registered with live secret | Provider dashboards | Developer | Not Started
21 | 5. Theme Activation | Flush permalinks | Settings > Permalinks saved | WP admin | Developer | Not Started
22 | 6. Cache Clearing | Purge LiteSpeed cache (all) | Purge confirmation | LiteSpeed | Developer | Not Started
23 | 6. Cache Clearing | Purge CDN / hosting cache if applicable | Fresh assets served (versioned URLs) | hPanel / CDN | Developer | Not Started
24 | 6. Cache Clearing | Disable maintenance mode | Public site visible | WP admin | Developer | Not Started
25 | 7. Smoke Testing | Homepage, article, category, author load (guest) | 200, correct layout | Browser | Developer | Not Started
26 | 7. Smoke Testing | Issue archive, single issue, flipbook, download | Works per access rules | Browser | Developer | Not Started
27 | 7. Smoke Testing | Login, register, reset, Google sign-in | All succeed | Browser | Developer | Not Started
28 | 7. Smoke Testing | Live payment test (low value) + webhook received | Tier activated; refund test transaction | Gateway | Developer | Not Started
29 | 7. Smoke Testing | Contact & lead forms | Stored + emailed | Browser | Developer | Not Started
30 | 7. Smoke Testing | Sample crawl of 200 legacy URLs | All 200, no 404 | Crawler | Developer | Not Started
31 | 8. Rollback Readiness | Rollback decision owner & go/no-go criteria agreed | Criteria documented (see Rollback Plan) | — | Developer | Not Started
32 | 8. Rollback Readiness | Backup files reachable & restore commands ready | Paths and commands in Notes | — | Developer | Not Started
33 | 8. Rollback Readiness | Go / No-Go decision recorded | Decision + time recorded | — | Developer | Not Started
34 | 9. Post-launch Monitoring | Resubmit sitemaps in Google Search Console | Sitemaps processed | GSC | Developer | Not Started
35 | 9. Post-launch Monitoring | Monitor PHP error log (24–48 h) | No fatal errors | debug.log / hPanel | Developer | Not Started
36 | 9. Post-launch Monitoring | Monitor Search Console coverage/404s (7 days) | No spike in 404s | GSC | Developer | Not Started
37 | 9. Post-launch Monitoring | Check Core Web Vitals on production | Targets met | PageSpeed | Developer | Not Started
38 | 9. Post-launch Monitoring | Compare post-launch row counts with pre-cutover | Counts identical | SQL | Developer | Not Started
39 | 9. Post-launch Monitoring | Lift content freeze; notify editors | Editors publishing normally | Email | Developer | Not Started
ROLLBACK PLAN (rehearsed in task P6-19 — record rehearsal time in Notes)
# | Trigger |  | Rollback action |  |  | Target time | Rehearsed? |  | Notes
1 | Fatal error / white screen after activation |  | Re-activate previous theme from WP admin or rename theme folder via SFTP; purge cache |  |  | < 5 min | Not Started
2 | Data corruption or missing content |  | Enable maintenance; restore pre-cutover DB dump; purge cache; verify row counts |  |  | < 30 min | Not Started
3 | Widespread 404s / permalink failure |  | Flush permalinks; if unresolved re-activate previous theme; restore .htaccess backup |  |  | < 10 min | Not Started
4 | Payments failing in live mode |  | Disable checkout (maintenance notice on subscribe page); switch webhooks back; keep site live |  |  | < 10 min | Not Started
5 | Severe performance degradation |  | Revert LiteSpeed settings export; disable new heavy features via settings; else theme rollback |  |  | < 15 min | Not Started
Go / No-Go rule: roll back if any P0 smoke test in Stage 7 fails and cannot be fixed within 30 minutes, if content/row counts differ from the pre-cutover record, or if payments cannot be confirmed in live mode (payments may instead be disabled while the site stays live).

## Risks & Blockers
RISKS & BLOCKERS REGISTER
Severity and Status are dropdowns. Open Critical/High risks are highlighted. Review daily during stand-up.
← Dashboard |  | Open: 18 · Open Critical: 3 · Open High: 8 · Realized: 0
Risk ID | Related Phase | Description | Severity | Likelihood | Impact | Mitigation | Owner | Status | Resolution | Date Raised
R-01 | All | Source Engineering Directive PDF was not available when this tracker was generated; detailed acceptance criteria may differ from the brief. | High | Possible | Missed or mis-specified requirements | Reconcile every task's Acceptance Criteria against the 13-page PDF on Day 1; add missing tasks in spare rows | Developer | Open |  | 2026-10-11
R-02 | All | Full scope (111 tasks) is very ambitious for one developer between 12 Oct and 1 Nov. | Critical | Likely | Deadline miss or quality loss | Watch the Dashboard Schedule Health daily; agree with client now which P2 items (e.g. Apple sign-in, print CSS, grid/list toggle, media kit gating) may move post-launch; protect P0 scope | Developer + Client | Open |  | 2026-10-11
R-03 | P6 | Very large WordPress backup (uploads) may exceed Hostinger limits/timeouts. | High | Possible | No restorable backup; cutover blocked | Split backup (DB, uploads by year, theme/plugins); use SSH tar/rsync; store off-server; verify checksums | Developer | Open |  | 2026-10-11
R-04 | P6 | Database import to staging/production may fail (size, max_allowed_packet, timeouts, charset utf8mb4 Arabic). | High | Possible | Corrupt Arabic text or incomplete DB | Use mysqldump/CLI import or chunked import; confirm utf8mb4; compare row counts | Developer | Open |  | 2026-10-11
R-05 | P6 | Hosting restrictions (no SSH/WP-CLI, PHP limits, cron, .htaccess rules) on Hostinger plan. | Medium | Possible | Slower migration; blocked PDF protection | Confirm plan capabilities Day 1 (P1-01); fallback to admin-based importer and PHP-served PDFs | Developer | Open |  | 2026-10-11
R-06 | P5 | Payment provider approval or live keys not ready by cutover. | Critical | Likely | Subscriptions cannot launch | Request Day 1 (P5-03); launch with subscriptions in sandbox-off/'coming soon' mode if not approved | Client | Open |  | 2026-10-11
R-07 | P5 | Google / Apple credentials delayed (Apple requires paid developer account + domain verification). | Medium | Possible | Social login missing at launch | Request Day 1; ship email login first; Apple as P2 | Client | Open |  | 2026-10-11
R-08 | P4 | 48 historical PDFs/covers incomplete or low quality. | High | Possible | Archive incomplete | Request Day 1 (P4-03); track missing list; launch with available issues clearly marked | Client | Open |  | 2026-10-11
R-09 | P4 | Large PDFs slow flipbook / exceed upload limits. | Medium | Possible | Poor reader UX | Compress PDFs, lazy-load PDF.js, increase upload limit or upload via SFTP | Developer | Open |  | 2026-10-11
R-10 | P3 | Legacy JNews shortcodes/meta embedded in 2,645 articles break after theme switch. | High | Possible | Broken article content, lost view counts | Audit on Day 2 (P6-04); add shortcode fallbacks; migrate view meta | Developer | Open |  | 2026-10-11
R-11 | P6 | Permalink/SEO regressions after replacing JNews. | Critical | Likely | Traffic loss | Baseline crawl, full URL validation, redirect map, post-launch GSC monitoring | Developer | Open |  | 2026-10-11
R-12 | All | Working directly on shared staging without local environment — accidental breakage without history. | Medium | Possible | Lost work / downtime of staging | Git repo for theme; daily DB snapshot of staging; small incremental deploys | Developer | Open |  | 2026-10-11
R-13 | All | Content published on production during development diverges from staging. | Medium | Possible | Lost posts at cutover | Theme-only deployment strategy (production DB kept); content freeze only during cutover window | Developer + Client | Open |  | 2026-10-11
R-14 | P6 | LiteSpeed caching of private pages (account, checkout) or stale homepage. | High | Possible | Data exposure / stale content | Exclude private URLs, vary on login cookie, purge on publish; test as guest & member | Developer | Open |  | 2026-10-11
R-15 | P5 | Webhook spoofing or duplicate events corrupt subscription state. | High | Possible | Revenue / access errors | Signature verification, idempotency keys, event log | Developer | Open |  | 2026-10-11
R-16 | All | Client feedback/approval delays (content for About/Advertise, UAT). | Medium | Possible | Schedule slip | Share staging link early (P2-24); set feedback deadlines; placeholders until content arrives | Client | Open |  | 2026-10-11
R-17 | All | Third-party plugin conflicts with new theme (SEO, LiteSpeed, forms). | Medium | Possible | Features break | Keep plugin set minimal; test each on staging; document versions | Developer | Open |  | 2026-10-11
R-18 | All | Single-developer availability (illness, fatigue) with no backup resource. | High | Possible | Deadline miss | Daily planner tracking, 6 h bug buffer, early escalation when daily variance appears | Developer | Open |  | 2026-10-11

## Requirement Map
REQUIREMENT TRACEABILITY MAP
Every requirement from the brief mapped to tracker tasks. Coverage updates as tasks complete.
← Dashboard
Req # | Phase | Requirement (from brief) | Mapped Task IDs | ƒ Tasks | ƒ Done | ƒ Coverage
REQ-01 | Phase 1 | Custom WordPress theme structure | P1-02 | 1 | 1 | ✓ Delivered
REQ-02 | Phase 1 | Theme initialization | P1-03 | 1 | 0 | 0 / 1 done
REQ-03 | Phase 1 | PHP templates and reusable components | P1-05, P1-06 | 2 | 0 | 0 / 2 done
REQ-04 | Phase 1 | CSS and Vanilla JS architecture | P1-04, P1-07, P1-08 | 3 | 0 | 0 / 3 done
REQ-05 | Phase 1 | RTL typography and responsive design | P1-09, P1-10 | 2 | 0 | 0 / 2 done
REQ-06 | Phase 1 | WordPress integration | P1-11, P1-12, P1-13 | 3 | 0 | 0 / 3 done
REQ-07 | Phase 1 | Query caching and Arabic date helpers | P1-14, P1-15 | 2 | 0 | 0 / 2 done
REQ-08 | Phase 2 | Homepage hero | P2-09 | 1 | 0 | 0 / 1 done
REQ-09 | Phase 2 | Breaking news ticker | P2-10 | 1 | 0 | 0 / 1 done
REQ-10 | Phase 2 | Magazine cover slider | P2-11 | 1 | 0 | 0 / 1 done
REQ-11 | Phase 2 | Chamber and opinion sections | P2-12, P2-13 | 2 | 0 | 0 / 2 done
REQ-12 | Phase 2 | Reports and article grids | P2-14, P2-15 | 2 | 0 | 0 / 2 done
REQ-13 | Phase 2 | Business, real estate, automotive, technology, healthcare, tourism sections | P2-16, P2-17, P2-18, P2-19, P2-20, P2-21 | 6 | 0 | 0 / 6 done
REQ-14 | Phase 2 | Most-read widget | P2-22 | 1 | 0 | 0 / 1 done
REQ-15 | Phase 2 | WordPress Customizer and Section Manager | P2-01, P2-02 | 2 | 0 | 0 / 2 done
REQ-16 | Phase 2 | Dynamic category/tag selection | P2-03 | 1 | 0 | 0 / 1 done
REQ-17 | Phase 2 | Post counts, sorting, offsets and manual post selection | P2-04, P2-05 | 2 | 0 | 0 / 2 done
REQ-18 | Phase 2 | Layout switching, section visibility and cache controls | P2-06, P2-07, P2-08 | 3 | 0 | 0 / 3 done
REQ-19 | Phase 3 | Single article template | P3-01, P3-03 | 2 | 0 | 0 / 2 done
REQ-20 | Phase 3 | Category archives | P3-09, P3-10 | 2 | 0 | 0 / 2 done
REQ-21 | Phase 3 | Article metadata | P3-02 | 1 | 0 | 0 / 1 done
REQ-22 | Phase 3 | Author profiles | P3-08 | 1 | 0 | 0 / 1 done
REQ-23 | Phase 3 | Reading progress bar | P3-04 | 1 | 0 | 0 / 1 done
REQ-24 | Phase 3 | Social sharing | P3-05 | 1 | 0 | 0 / 1 done
REQ-25 | Phase 3 | Advertisement injection | P3-06 | 1 | 0 | 0 / 1 done
REQ-26 | Phase 3 | Related articles | P3-07 | 1 | 0 | 0 / 1 done
REQ-27 | Phase 3 | AJAX filtering | P3-11 | 1 | 0 | 0 / 1 done
REQ-28 | Phase 3 | Grid/list switching | P3-12 | 1 | 0 | 0 / 1 done
REQ-29 | Phase 3 | Pagination | P3-13 | 1 | 0 | 0 / 1 done
REQ-30 | Phase 3 | Print stylesheet | P3-14 | 1 | 0 | 0 / 1 done
REQ-31 | Phase 3 | SEO compatibility | P3-15 | 1 | 0 | 0 / 1 done
REQ-32 | Phase 4 | Magazine issue custom post type | P4-01, P4-02 | 2 | 0 | 0 / 2 done
REQ-33 | Phase 4 | Issue archive | P4-06 | 1 | 0 | 0 / 1 done
REQ-34 | Phase 4 | Single issue page | P4-08 | 1 | 0 | 0 / 1 done
REQ-35 | Phase 4 | Historical issue migration | P4-03, P4-04 | 2 | 0 | 0 / 2 done
REQ-36 | Phase 4 | All 48 magazine issues | P4-04, P4-12 | 2 | 0 | 0 / 2 done
REQ-37 | Phase 4 | Cover images | P4-05 | 1 | 0 | 0 / 1 done
REQ-38 | Phase 4 | Year and decade filtering | P4-07 | 1 | 0 | 0 / 1 done
REQ-39 | Phase 4 | Flipbook reader | P4-09 | 1 | 0 | 0 / 1 done
REQ-40 | Phase 4 | PDF downloads | P4-10 | 1 | 0 | 0 / 1 done
REQ-41 | Phase 4 | Access restrictions | P4-11 | 1 | 0 | 0 / 1 done
REQ-42 | Phase 5 | Login, registration and password reset | P5-04 | 1 | 0 | 0 / 1 done
REQ-43 | Phase 5 | Google and Apple authentication | P5-01, P5-02, P5-05, P5-06 | 4 | 0 | 0 / 4 done
REQ-44 | Phase 5 | Member dashboard | P5-11 | 1 | 0 | 0 / 1 done
REQ-45 | Phase 5 | Security and rate limiting | P5-12 | 1 | 0 | 0 / 1 done
REQ-46 | Phase 5 | Subscription tiers | P5-07, P5-10 | 2 | 0 | 0 / 2 done
REQ-47 | Phase 5 | Payment gateway integration | P5-03, P5-08 | 2 | 0 | 0 / 2 done
REQ-48 | Phase 5 | Payment webhooks | P5-09 | 1 | 0 | 0 / 1 done
REQ-49 | Phase 5 | Advertising page | P5-14 | 1 | 0 | 0 / 1 done
REQ-50 | Phase 5 | Advertising rate calculator | P5-15 | 1 | 0 | 0 / 1 done
REQ-51 | Phase 5 | Media kit | P5-16 | 1 | 0 | 0 / 1 done
REQ-52 | Phase 5 | Lead capture forms | P5-17 | 1 | 0 | 0 / 1 done
REQ-53 | Phase 5 | About page | P5-18 | 1 | 0 | 0 / 1 done
REQ-54 | Phase 5 | Contact page | P5-19, P5-13 | 2 | 0 | 0 / 2 done
REQ-55 | Phase 5 | Editorial roles and permissions | P5-20 | 1 | 0 | 0 / 1 done
REQ-56 | Phase 6 | Database backup and audit | P6-01, P6-03, P6-20 | 3 | 0 | 0 / 3 done
REQ-57 | Phase 6 | Legacy JNews dependency review | P6-04 | 1 | 0 | 0 / 1 done
REQ-58 | Phase 6 | Safe database optimization | P6-07 | 1 | 0 | 0 / 1 done
REQ-59 | Phase 6 | SEO preservation | P6-06, P6-09, P6-10 | 3 | 0 | 0 / 3 done
REQ-60 | Phase 6 | Validation of all 2,645 article URLs | P6-05, P6-08 | 2 | 0 | 0 / 2 done
REQ-61 | Phase 6 | Performance optimization | P6-11 | 1 | 0 | 0 / 1 done
REQ-62 | Phase 6 | LiteSpeed caching | P6-12 | 1 | 0 | 0 / 1 done
REQ-63 | Phase 6 | Responsive and cross-browser testing | P6-13, P6-14, P6-16 | 3 | 0 | 0 / 3 done
REQ-64 | Phase 6 | Security verification | P6-15 | 1 | 0 | 0 / 1 done
REQ-65 | Phase 6 | Deployment readiness | P6-02, P6-17, P6-18 | 3 | 0 | 0 / 3 done
REQ-66 | Phase 6 | Rollback plan | P6-19 | 1 | 0 | 0 / 1 done
REQ-67 | Phase 6 | Production cutover and post-launch verification | P6-21, P6-22 | 2 | 0 | 0 / 2 done

## Lists (hidden)
Status | Priority | Environment | Phase | ExtReq | TestResult | QAResult | DeployStatus | Severity | RiskStatus | Likelihood | ProjectStart | Completion | Module | Blocker | TaskNotes | Dates | Owner | RiskPhase | Device | QANotes | DeployNotes | Resolution | Stage | Area
Not Started | P0 | Staging (Hostinger) | Phase 1 | None | Not Tested | Not Run | Not Started | Critical | Open | Very Likely | 2026-10-12 | 0% | Staging Setup | None | Needs client review | 2026-10-01 | Developer | All | Desktop Chrome | No defect | OK | Mitigation in place | 1. Staging Verification | Template 1: Homepage
In Progress | P1 | Production | Phase 2 | Credentials | Pass | Pass | In Progress | High | Monitoring | Likely |  | 10% | Theme Scaffold | Waiting on credentials | Waiting for feedback | 2026-10-02 | Client (O2 Nations) | P1 | Desktop + Mobile | Minor visual issue – logged | OK – with minor issue | Client approved deferral | 2. Full Backup | Template 2: Single Article
Blocked | P2 | Staging + Production | Phase 3 | Payment Approval | Fail | Fail | Done | Medium | Mitigated | Possible |  | 20% | Theme Initialization | Waiting on payment provider | Reconcile with Engineering Directive PDF | 2026-10-03 | Developer + Client | P2 | iPhone Safari, Android Chrome | Functional bug – logged | Skipped (N/A) | Resolved – no impact | 3. Database Backup | Template 3: Category Archive
In Review |  | External / Third-party | Phase 4 | Historical Assets | Partial | Blocked | Failed | Low | Realized | Unlikely |  | 30% | Asset Pipeline | Waiting on client content / feedback | Partially done – continue tomorrow | 2026-10-04 | Hosting (Hostinger) | P3 | iPhone + Android + Desktop | Blocked by open task | Failed – rollback triggered | Accepted risk | 4. SEO Comparison | Template 4: Author Profile
Testing |  |  | Phase 5 | Server Access | N/A | N/A | N/A |  | Closed |  |  | 40% | PHP Templates | Waiting on historical PDFs / covers | Deferred to post-launch (client approved) | 2026-10-05 | Payment Provider | P4 | Desktop | Retest after fix | Repeated successfully | Escalated to client | 5. Theme Activation | Template 5: Issues Archive
Completed |  |  | Phase 6 | Client Content | [7 empty] | 50% | Components | Hosting / server access issue | Reopened after QA | 2026-10-06 |  | P5 | Crawler | Fixed & retested |  |  | 6. Cache Clearing | Template 6: Single Issue
[12 empty] | 60% | CSS Architecture | Dependency task not finished | Done – pending retest | 2026-10-07 |  | P6 | PageSpeed Insights mobile |  |  |  | 7. Smoke Testing | Template 7: Advertise
[12 empty] | 70% | Vanilla JS | Bug found in testing |  | 2026-10-08 |  |  | Chrome (latest, Windows/macOS) |  |  |  | 8. Rollback Readiness | Template 8: About
[12 empty] | 80% | RTL Typography | Plugin / theme conflict |  | 2026-10-09 |  |  | Safari (macOS) |  |  |  | 9. Post-launch Monitoring | Template 9: Contact
[12 empty] | 90% | Responsive Design | Performance issue |  | 2026-10-10 |  |  | Safari (iOS) |  |  |  |  | WordPress Dynamic Content
[12 empty] | 100% | Header & Navigation | Other (see Notes) |  | 2026-10-11 |  |  | Firefox (latest) |  |  |  |  | RTL Layout
[13 empty] | Footer |  |  | 2026-10-12 |  |  | Edge (latest) |  |  |  |  | Mobile Responsiveness
[13 empty] | WordPress Integration |  |  | 2026-10-13 |  |  | Samsung Internet (Android) |  |  |  |  | Authentication
[13 empty] | Query Caching |  |  | 2026-10-14 | [7 empty] | Subscription Functionality
[13 empty] | Date Helpers |  |  | 2026-10-15 | [7 empty] | Payment Workflows
[13 empty] | Media |  |  | 2026-10-16 | [7 empty] | SEO Metadata
[13 empty] | Phase QA |  |  | 2026-10-17 | [7 empty] | Existing Article URLs
[13 empty] | Section Manager |  |  | 2026-10-18 | [7 empty] | Performance
[13 empty] | Customizer |  |  | 2026-10-19 | [7 empty] | Security
[13 empty] | Customizer Controls |  |  | 2026-10-20 | [7 empty] | Contact Forms
[13 empty] | Cache Controls |  |  | 2026-10-21 | [7 empty] | Magazine PDFs
[13 empty] | Homepage Sections |  |  | 2026-10-22 | [7 empty] | Browser Compatibility
[13 empty] | Sector Sections |  |  | 2026-10-23
[13 empty] | Most Read |  |  | 2026-10-24
[13 empty] | AdOps |  |  | 2026-10-25
[13 empty] | Single Article |  |  | 2026-10-26
[13 empty] | Article Metadata |  |  | 2026-10-27
[13 empty] | Legacy Content |  |  | 2026-10-28
[13 empty] | Engagement |  |  | 2026-10-29
[13 empty] | Author Profiles |  |  | 2026-10-30
[13 empty] | Category Archives |  |  | 2026-10-31
[13 empty] | Taxonomy |  |  | 2026-11-01
[13 empty] | AJAX Filtering |  |  | 2026-11-02
[13 empty] | Archive UX |  |  | 2026-11-03
[13 empty] | Pagination |  |  | 2026-11-04
[13 empty] | Print |  |  | 2026-11-05
[13 empty] | SEO |  |  | 2026-11-06
[13 empty] | CPT Engine |  |  | 2026-11-07
[13 empty] | Historical Assets |  |  | 2026-11-08
[13 empty] | Migration |  |  | 2026-11-09
[13 empty] | Cover Images |  |  | 2026-11-10
[13 empty] | Issue Archive |  |  | 2026-11-11
[13 empty] | Single Issue |  |  | 2026-11-12
[13 empty] | Flipbook |  |  | 2026-11-13
[13 empty] | PDF Downloads |  |  | 2026-11-14
[13 empty] | Access Control |  |  | 2026-11-15
[13 empty] | Credentials |  |  | 2026-11-16
[13 empty] | Payments |  |  | 2026-11-17
[13 empty] | Authentication |  |  | 2026-11-18
[13 empty] | Subscriptions |  |  | 2026-11-19
[13 empty] | Member Dashboard |  |  | 2026-11-20
[13 empty] | Security |  |  | 2026-11-21
[13 empty] | Email |  |  | 2026-11-22
[13 empty] | Leads |  |  | 2026-11-23
[13 empty] | Pages |  |  | 2026-11-24
[13 empty] | Roles |  |  | 2026-11-25
[13 empty] | Backup |  |  | 2026-11-26
[13 empty] | DB Audit |  |  | 2026-11-27
[13 empty] | JNews Review |  |  | 2026-11-28
[13 empty] | URL Inventory |  |  | 2026-11-29
[13 empty] | SEO Baseline |  |  | 2026-11-30
DB Optimization
URL Validation
Performance
Caching
Testing
Bug Fixing
Readiness
Rollback
Cutover
Post-launch